## User's Guide
Closeout ERR Last updated: 06/01/2011
Armenia: Rural Road Rehabilitation
ERR Type | Original ERR | Closeout ERR
Date | 2005-11-17 | 2011-06-01
Amount of MCC funds | $67.1 million | $4.7 million
Project description | -Rehabilitate up to 943 km of high priority rural roads connecting to the national highway network, consisting of 85 road segments throughout the country and amounting to 321 km of national roads and 622 km of local roads. -All rehabilitation works will be on existing alignments and will include pavement rehabilitation, improvements to up to 19 bridges, drainage facilities, and road safety features. | -Following the MCC Board of Directors' meeting in June 2009, MCC did not resume funding for this project. Prior to this, two sections of road on the N-17 route were successfully completed, totaling about 24 kilometers
Benefit streams included in ERR | Savings on vehicle operating costs | Savings on vehicle operating costs
| Value of time savings | Value of time savings
Costs included in ERR (other than costs borne by MCC) | Maintenance costs | Maintenance costs
Estimated ERR and time horizon | 25.9% over 30 years | 17.6% over 20 years
Worksheets included in this file
Project Description
Gives a summary of the project, a list of components, and states the economic rationale for the project.
ERR & Sensitivity Analysis
This worksheet highlights key assumptions and summarizes how the ERR may change due to varying costs and benefits.
Cost-Benefit Summary
This worksheet presents the aggregated costs and benefits from the On-Farm and Cool Chain activities year-by-year, calculating a combined ERR

## Project Description
Closeout ERR Last updated: 06/01/2011
Armenia: Rural Road Rehabilitation
Project Design History
Original Project
MCC Funding was to be used to rehabilitate up to 943 km of high priority rural roads connecting to the national highway network, consisting of 85 road segments throughout the country and amounting to 321 km of national roads and 622 km of local roads. All rehabilitation works was planned for existing alignments to include pavement rehabilitation, improvements to up to 19 bridges, drainage facilities, and road safety features.
MCA-Armenia selected roads that were eligible for MCC funding according to the following criteria:
1. Have an economic rate of return at least equal to 12.5%, calculated in a manner acceptable to MCC and based on a feasibility study and final design.
2. Conform to Government requirements and MCC’s Environmental Guidelines.
3. Conform to the World Bank policy on Involuntary Resettlement, where relevant.
MCC Funding was also to be provided to ARD to conduct a technical audit of its existing performance based maintenance contracts and for technical assistance to create a long-term road maintenance strategic plan.
Closeout
Following the June 2009 meeting of the MCC Board of Directors, MCC did not resume funding for road construction and rehabilitation under the compact due to concerns about the status of democratic governance in Armenia. However, about 25 kilometers of pilot roads were completed prior to this decision and design studies were completed for 570 km. To date, 150 kilometers of MCC-funded road designs are now being funded by the World Bank.
Current Project Components
1. Rehabilitation of two segments of highway, both located on the R-17. 2. Design studies completed for 570 km of rural roads.
Economic Rationale
Road transport plays a vital role in Armenia's regional and national economic development. At the time of compact signing, nearly 90% of domestic freight and more than 95% of passenger journeys utilize roads. The ERRs thus reflect monetized economic benefits of the proposed and actual rehabilitation of the rural road network; these calculations were computed using the Highway Development and Management Model, v. 4 (HDM-4)1, a state-of-the-art software package for evaluating economic rates of return. The benefits are attributable to (1) operating cost savings for vehicles and wear and tear on the roadbed, and (2) travel time-savings, as improvements in road condition permit higher average driving speeds. As originally conceived, it was estimated that this Project would result in reduction in transportation costs of $20 milion a year beginning five years after material project benefits are realized.
A key input into the HDM model is current levels of traffic. Traffic surveys were not completed on all proposed road links, so estimates for current traffic were made based on vehicle ownership and agricultural production levels. Each road link' s ERR was compared to a hurdle rate of 12.5%, Armenia's average real growth rate over the past three years. All of the roads that exceeded this hurdle were included in the original program. For the other roads, a downgrade in the level of service was analyzed and if the resulting ERR was high enough, those roads were included as well. Some links, even at the lowest level of service (gravel), did not have ERRs above the hurdle and were cut from the original program. A few exceptions were made for roads that provide the lifeline connection to communities included in the Irrigated Agriculture Project.
These reductions in the cost and time of transport translate to enhanced economic growth via reductions in the cost of production and distribution and by making other factors of production more productive for enterprises and individual farmers alike. At the macroeconomic level, there is significant empirical evidence of a positive correlation between road networks on the one hand and GDP per capita or growth rates on the other.
1 The Highway Development and Management (HDM-4) model was originally developed by the World Bank and is now widely used in highway planning. HDM estimates the total costs for different scenarios in road construction, maintenance and use so that users can determine the best strategy for road projects.

## ERR & Sensitivity Analysis
Closeout ERR Last updated: 06/01/2011
Armenia: Rural Road Rehabilitation
ERR and sensitivity analysis |  |  |  |  | Last updated: 11/17/2005
Change the "User Input" cells in the table below to see the effect on the compact's Economic Rate of Return (ERR) and net benefits (see chart below). To reset all values to the default MCC estimates, click the "Reset Parameters" button at right. Be sure to reset all summary parameters to their original values ("MCC Estimate" values) before changing specific parameters.
Parameter type | Description of key parameters | Parameter values
|  | User Input | MCC Estimate | Plausible range | Values used in ERR computation | All summary parameters set to initial values?
Summary | Actual costs as a percentage of estimated costs | 100% | 100% | 80 - 120% | 100% | Y
Summary | Actual benefits as a percentage of estimated benefits | 100% | 100% | 80 - 120% | 100%
More Info
| Economic rate of return (ERR): | 17.63% |  |  |  | Project Description
| MCC Estimated ERRs: |  | Original | Closeout |  | User's Guide
|  | ERR | 25.9% | 17.6%
|  | Date | 2005-11-17 | 2011-06-01
| Present Value (PV) of Benefits: | 8248001.4763
| Present Value (PV) of MCC Costs: | 6009595.5547
Reset Parameters

## Cost-Benefit Summary
0 | [7 empty] | Closeout ERR Last updated: 06/01/2011
Change these parameters in ERR & Sensitivity Analysis tab
|  | Actual costs as percentage of estimated costs |  |  |  |  | 100%
|  | Actual benefits as percentage of estimated benefits |  |  |  |  | 100%
Cost-Benefit Summary
| Year | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Total project benefits (amounts in $ million)
|  | 0 | 0 | 1.2169 | 1.2169 | 1.2169 | 1.2169 | 1.2169 | 1.2169 | 1.2169 | 1.2169 | 1.2169 | 1.2169 | 1.2169 | 1.2169 | 1.2169 | 1.2169 | 1.2169 | 1.2169 | 1.2169 | 1.2169
Total project costs (amounts in $ million)
|  | 0 | 5.6606 | 0 | 0 | 0 | 0 | 0 | 1.5156 | 0 | 0 | 0 | 0 | 0 | 1.5156 | 0 | 0 | 0 | 0 | 0 | 1.5156
Total project net benefits (amounts in $ million)
|  | 0 | -5.6606 | 1.2169 | 1.2169 | 1.2169 | 1.2169 | 1.2169 | -0.2987 | 1.2169 | 1.2169 | 1.2169 | 1.2169 | 1.2169 | -0.2987 | 1.2169 | 1.2169 | 1.2169 | 1.2169 | 1.2169 | -0.2987
| Project ERR | 17.63%
| PV (Benefits) | 8.248
| PV (Costs) | 6.0096
| Discount Rate | 10%
Background Information
[12 empty] | Numbers of years in which benefits accrue: | 19
[12 empty] | Periodic maintenance fraction | 45%
Section: R-17 (49+300-60+960)
Alternative: Project Alt vs Base Alternative
|  | Increase in Road Agency Costs |  |  | Savings in MT VOC | Savings in MT Travel Time Cost | Savings in NMT Travel & Operating Cost | Reduction in Accident Cost | Net Exogenous Benefits | Net Economic Benefits (NPV)
[5 empty] | Savings in MT VOC |  |  | Reduction in Accident Cost | Net Exogenous Benefits | Net Economic Benefits (NPV)
|  | Capital | Recurrent | Special
| Undiscounted | 5.0322 | 0 | 0 | 9.5334 | 0.82969 | 0 | 0 | 0 | 5.3309
| Discounted | 2.6285 | 0 | 0 | 2.8513 | 0.2527 | 0 | 0 | 0 | 0.47556
[5 empty] | Section: R17(60+960-73+780) | [6 empty] | Numbers of years in which benefits accrue: | 19
[5 empty] | Alternative: Project Alt vs Base Alternative | [6 empty] | Periodic maintenance fraction | 44.1%
|  | Increase in Road Agency Costs |  |  | Savings in MT VOC | Savings in MT Travel Time Cost | Savings in NMT Travel & Operating Cost | Reduction in Accident Cost | Net Exogenous Benefits | Net Economic Benefits (NPV)
[5 empty] | Savings in MT VOC |  |  | Reduction in Accident Cost | Net Exogenous Benefits | Net Economic Benefits (NPV)
|  | Capital | Recurrent | Special
| Undiscounted | 5.1751 | 0 | 0 | 10.62 | 0.92069 | 0 | 0 | 0 | 6.3635
| Discounted | 2.7032 | 0 | 0 | 3.17 | 0.28049 | 0 | 0 | 0 | 0.7426
Notional cashflows consistent with tables above
Section: R-17 (49+300-60+960) (amounts in $ million)
Year
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
| Total costs | Year 1: -2.7677; Year 7: -0.75483; Year 13: -0.75483; Year 19: -0.75483
| Total benefits |  | 0.54542 | 0.54542 | 0.54542 | 0.54542 | 0.54542 | 0.54542 | 0.54542 | 0.54542 | 0.54542 | 0.54542 | 0.54542 | 0.54542 | 0.54542 | 0.54542 | 0.54542 | 0.54542 | 0.54542 | 0.54542 | 0.54542
| Net benefits | -2.7677 | 0.54542 | 0.54542 | 0.54542 | 0.54542 | 0.54542 | -0.20941 | 0.54542 | 0.54542 | 0.54542 | 0.54542 | 0.54542 | -0.20941 | 0.54542 | 0.54542 | 0.54542 | 0.54542 | 0.54542 | -0.20941 | 0.54542
Section: R17(60+960-73+780) (amounts in $ million)
Year
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
| Total costs | Year 1: -2.8929; Year 7: -0.76075; Year 13: -0.76075; Year 19: -0.76075
| Total benefits |  | 0.6074 | 0.6074 | 0.6074 | 0.6074 | 0.6074 | 0.6074 | 0.6074 | 0.6074 | 0.6074 | 0.6074 | 0.6074 | 0.6074 | 0.6074 | 0.6074 | 0.6074 | 0.6074 | 0.6074 | 0.6074 | 0.6074
| Net benefits | -2.8929 | 0.6074 | 0.6074 | 0.6074 | 0.6074 | 0.6074 | -0.15334 | 0.6074 | 0.6074 | 0.6074 | 0.6074 | 0.6074 | -0.15334 | 0.6074 | 0.6074 | 0.6074 | 0.6074 | 0.6074 | -0.15334 | 0.6074
| The flows below replicate the flows given above, but reflect the fact that roads were actually built in Y2, so flows are moved out 1 year | Year 14: Numbers of years in which benefits accrue:; Year 15: 18
Section: R-17 (49+300-60+960) (amounts in $ million)
Year
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
| Total costs | Year 2: -2.7677; Year 8: -0.75483; Year 14: -0.75483; Year 20: -0.75483
| Total benefits |  |  | 0.57572 | 0.57572 | 0.57572 | 0.57572 | 0.57572 | 0.57572 | 0.57572 | 0.57572 | 0.57572 | 0.57572 | 0.57572 | 0.57572 | 0.57572 | 0.57572 | 0.57572 | 0.57572 | 0.57572 | 0.57572
| Savings in MT VOC |  |  | 0.52963 | 0.52963 | 0.52963 | 0.52963 | 0.52963 | 0.52963 | 0.52963 | 0.52963 | 0.52963 | 0.52963 | 0.52963 | 0.52963 | 0.52963 | 0.52963 | 0.52963 | 0.52963 | 0.52963 | 0.52963
| Savings in MT Travel Time Cost |  |  | 0.046094 | 0.046094 | 0.046094 | 0.046094 | 0.046094 | 0.046094 | 0.046094 | 0.046094 | 0.046094 | 0.046094 | 0.046094 | 0.046094 | 0.046094 | 0.046094 | 0.046094 | 0.046094 | 0.046094 | 0.046094
| Net benefits | 0 | -2.7677 | 0.57572 | 0.57572 | 0.57572 | 0.57572 | 0.57572 | -0.1791 | 0.57572 | 0.57572 | 0.57572 | 0.57572 | 0.57572 | -0.1791 | 0.57572 | 0.57572 | 0.57572 | 0.57572 | 0.57572 | -0.1791
| ERR | Year 1: 16.71%
Section: R17(60+960-73+780) (amounts in $ million)
Year
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
| Total costs | Year 2: -2.8929; Year 8: -0.76075; Year 14: -0.76075; Year 20: -0.76075
| Total benefits |  |  | 0.64115 | 0.64115 | 0.64115 | 0.64115 | 0.64115 | 0.64115 | 0.64115 | 0.64115 | 0.64115 | 0.64115 | 0.64115 | 0.64115 | 0.64115 | 0.64115 | 0.64115 | 0.64115 | 0.64115 | 0.64115
| Savings in MT VOC |  |  | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59
| Savings in MT Travel Time Cost |  |  | 0.051149 | 0.051149 | 0.051149 | 0.051149 | 0.051149 | 0.051149 | 0.051149 | 0.051149 | 0.051149 | 0.051149 | 0.051149 | 0.051149 | 0.051149 | 0.051149 | 0.051149 | 0.051149 | 0.051149 | 0.051149
| Net benefits | 0 | -2.8929 | 0.64115 | 0.64115 | 0.64115 | 0.64115 | 0.64115 | -0.1196 | 0.64115 | 0.64115 | 0.64115 | 0.64115 | 0.64115 | -0.1196 | 0.64115 | 0.64115 | 0.64115 | 0.64115 | 0.64115 | -0.1196
| ERR | Year 1: 18.5%