## Cover Page
Mongolia: Roads Project
Choir-Sainshand Road Activity
ERR Version | Original ERR | Closeout ERR
Date of ERR | 2009-11-01 | 2013-03-01
Amount of MCC funds | $ 68.4m | $ 74.8 m
Project Description | The original project consisted of three investments: construction of a 176 km segment of a north-south road extending to the border with China, replacement of a major bridge in Ulaanbaatar (sometimes referred to as "UB"), and a rehabilitation of a road linking the capital to Nalaikh and the main north-south road. | Due to termination of the first Choir-Sainshand road contract and resulting cost increases as well as failed procurements for the bridge and connecting road project, rescoping removed the Bayanzurkh bridge and the UB-Nalaikh road from the compact investment program.
Benefit streams included in ERR | Road user cost savings, including the opportunity cost of time in travel | Road user cost savings, including the opportunity cost of time in travel
Costs included in ERR (not borne by MCC) | Total investment costs and incremental road maintenance costs. | Total investment costs and incremental road maintenance costs.
ERR estimations and time horizon | 17.0% over 20 years for the Choir-Sainshand road; 20% for the Bayanzurch bridge and 20% for the UB-Nalaikh road. | 9.4% over 20 years (Choir-Sainshand road only)
Table of Contents
Project Description
CS Cost Benefit Model
GDP Growth
QDRP Excerpt
Poverty Scorecard

## Project Description
Mongolia: Roads Project
Choir-Sainshand Road Activity
Original Activity Design
The logic of the road investments argued that proposed development and rehabilitation of the specified infrastructure would facilitate private sector activity. Conditions of the Bayanzurkh bridge required a costly diversion of commercial traffic. The Bayanzurkh – Nalaikh road segment connected with the artery heading towards the southern border. From official accounts, the segment carried a large volume of traffic, which by Government estimates was growing at a rate of about 6 percent per annum. The Choir-Sainshand road segment, following completion of the Sainshand-Zamiin Uud segment financed by the Asian Development Bank, was the remaining link of a north-south road nexus connecting Russia and China. The road investment in principle should lower the transport costs of goods flowing across the border, including the costs of transit trade between Russia and China, as well as the costs of moving domestic raw materials and manufactures (such as those associated with the development of a planned industrial park in Sainshand). As is typical for the analysis of road investment projects, estimates of reductions in vehicle operating costs, based on the composition of traffic and changes in road use following investment, served as proxies of changes in income that improvements in infrastructure might introduce for consumers of transport services (for producers as well as for individuals).
Activity Components
The Project originally consisted of three components: 1) completion of a 176 km section of the North-South Corridor road under construction from the town of Choir to Zamiin Uud near the border with China. The segment fell between Choir and Sainshand (the Asian Development Bank was engaged in construction of the remaining length to Zamiin Uud); 2) rehabilitation of a 17.5 km connecting Ulannbaatar to Nalaikh; and 3) the replacement of the Bayanzurkh bridge in Ulaanbaatar with the rehabiliation of 3.4 km of road leading to and from it.
Economic Rationale
The analysis of the Choir-Sainshand road was based on the work of an earlier, well-executed feasibility study for the length of the N/S road that was completed in 2004 and provided suitable updates of key parameters and assumptions where feasible to do so. These principally concerned the basis for projecting future growth in traffic. To simplify due diligence, the analysis accepted earlier determinations of traffic composition based on O-D surveys, and recast unit vehicle operating cost savings in current prices. The task at hand was then to revisit the data and assumptions underlying the feasibility study projections of traffic growth. The Lead Economist had to base the analysis of the Choir-Sainshand road on data provided by Government: projected traffic volumes were not independently assessed. The analysis also relied on a MCC staff's assessment of the investment cost estimates. Compared to road construction projects in other MCC compacts, the capital costs of road construction in Mongolia appeared low. In this instance the expected returns to the investment were estimated to fall anywhere between 11 and 26 percent, depending upon the possible completion and performance of an industrial park in Sainshand. For further discussion, including sensitivity analysis, see the text of the IM. The Government proposed the Bayanzurkh bridge and Bayanzurkh-Nalaikh projects for MCC financing without accompanying economic assessments. Apart from investment costs, which were vetted by MCC staff, the principal assumptions of the analyses concerned estimates of future traffic growth. These were provided by Government and could not be validated. The preliminary assessments of these two proposals suggest that returns could exceed 12 percent; although, the ERRs could fall within wide ranges of equally probable values. In view of the firmness of traffic growth projections and their relative importance for establishing an acceptable rate of return, of the three proposed investments, the Bayanzurkh bridge investment was considered the least speculative followed by the Bayanzurkh-Nalaikh road segment and the construction of the Choir-Sainshand segment of the north-south road. Normally the population residing within a defined catchment area of a road is identified as the primary beneficiaries of a development. The situation is different in Mongolia given the sparseness of the population. Most beneficiaries of the Choir-Sainshand and Bayanzurkh-Nalaikk road segments, for example, are expected to be located elsewhere in Mongolia, presumably within the urban agglomeration of Ulaanbaator.
For the Choir-Sainshand road, the analysis considered estimating returns with and without the planned industrial park based on economic parameters provided in the earlier feasibility report. These parameters include traffic composition and road user savings (based on vehicle operating costs and the opportunity cost of time spent in travel) as a function of road roughness. Vehicle operating costs and theoretical travel speeds were generated from the algorithms of the HDM-4 software. The basis of these parameter estimates is transparent and in principle replicable. Nevertheless, they appear higher than more recent estimates of traffic-based benefits for new roads in Mongolia. The sensitivity of the results to changes traffic volumes and cost savings per trip should guide expectations regarding the uncertainty of feasible returns.
In the absence of an industrial park normal traffic along tracts marking the prospective route Choir-Sainshand road is expected to reach the equivalent of more than 161 vehicles per day (Annual Average Daily Traffic). Upon completion of the road, traffic volume, based on Government data is expected to jump by over 800 vehicles per day and grow thereafter at a rate around of about 7 percent per year[1]. Using these traffic projections the estimated economic return to the investment is estimated at about 11 percent.
In the event of the construction of an industrial park at Sainshand, with completion of construction coinciding with the completion of the road, Government estimates suggest that the incremental increase in traffic volume in the year following the road investment would jump by close over 1000 vehicles per day. Traffic volume then grows by rates ranging between 7 to 29 percent per year over the next four years and slows to about 3 percent annual growth from the year 2018 onwards. In this scenario the estimated return to the investment approaches 26 percent.
Without additional information on the completion and operation of an industrial park at Sainshand, the most that one can state at this point is that there is that the return is likely to fall in a range between 11 and 26 percent. Any outcome in this range was considered equally likely.
The analysis of the Bayanzurkh Bridge estimated the benefits of avoiding the diversion of heavy trucks and vehicles from the bridge. The diversion forces trucks and other heavy vehicles to travel 70 kilometres over sections of roads or tracts that are in very poor condition. The overall net increase in travelled distance, from the point of the diversion on the road south of the bridge to the destination in UB was estimated to be about 35 kilometres in the analysis. In addition to longer travel times there are significant increases in vehicle operating costs. Estimated economic benefits per trip by type of vehicle are comparable to those employed in the analysis of the Choir-Sainshand road investment. As in the former investment, the estimated ERR will depend upon anticipated growth in traffic on the transport artery in which the bridge is embedded. Government projects traffic volume on the route from UB to Zamin Uud to reach about 2200 vehicles per day in the year 2010 and to grow annually by about 6 percent. These estimates appear to anticipate higher levels of economic activity in the south of the country. On this basis the point estimate for the ERR to the proposed investment would be 20 percent. As these traffic projects have not been validated, and actual construction costs typically exceed study estimates, it is reasonable to judge that the probability that the true ERR is less than 20% is greater than the probability that the return is higher than 20%.
The analysis of the Bayanzurkh-Nalaikh segment mirrored the analysis of the Bayanzurkh Bridge project and applied the same caveats regarding expected returns. Given Government data on traffic on the UB-Zamiin Uud route, which connects to the Bayanzurkh-Nalaikh segment and is thus a determinant of flow on the segment, the upper bound to the return on the proposed investment is estimated to be about 21 percent if the Bayanzurkh Bridge is rehabilitated and 19 percent if the bridge investment does not occur. On the basis of arguments similar to those applied to the analysis of the bridge, it appeared likely that the ERR for the investment would fall within the range of 12 and 19 percent.
Closeout Summary
Following approval of the road project, increases in the cost of works for the N/S road led to a decision to re-allocate compact funds from the Bayanzurkh bridge and the UB-Nalaikh road to finance work on the Choir-Sainshand segment. These two investments of the project were dropped entirely. Investments costs for the Choir-Sainshand road had increased by more than 60%.
[1] In the earlier feasibility study traffic increased by about 560 vehicles and grew at a rate of about 5 percent per annum.
Last Updated: 3/1/2013

## GDP growth
|  | GDP Growth | [7 empty] | Last Updated: 3/1/2013
Country Name | Country Code | Indicator Name | Indicator Code | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016
Mongolia | MNG | GDP (constant 2000 US$) | NY.GDP.MKTP.KD | 1136896162.1422 | 1170465415.006 | 1225863291.0569 | 1311730534.9808 | 1451107229.3903 | 1556365693.0225 | 1689531996.1799 | 1862675511.534 | 2028460485.7537 | 2002727457.4926 | 2130204298.2709
Mongolia | MNG | GDP (constant LCU) | NY.GDP.MKTP.KN | 2221690265271 | 2.2873e+12 | 2.3955e+12 | 2.5633e+12 | 2.8357e+12 | 3.0414e+12 | 3.3016e+12 | 3.64e+12 | 3.964e+12 | 3.9137e+12 | 4.1628e+12
Mongolia | MNG | GDP (current LCU) | NY.GDP.MKTP.CN | 1.2241e+12 | 1.3919e+12 | 1.5506e+12 | 1.8291e+12 | 2.3612e+12 | 3.0414e+12 | 4.0276e+12 | 4.9566e+12 | 6.5556e+12 | 6.5906e+12 | 8.4145e+12
Mongolia | MNG | GDP (current US$) | NY.GDP.MKTP.CD | 1136896162.1422 | 1267997923.0327 | 1396555772.0379 | 1595297301.4565 | 1992066758.8442 | 2523359940.7121 | 3395917892.1926 | 4234894168.1566 | 5623236707.5247 | 4583834427.3647 | 6200357070.1148
|  | GDP deflator (% change) |  | Last Updated: 3/1/2013 2011: 14.1%; Last Updated: 3/1/2013 2012: 8.9%; Last Updated: 3/1/2013 2013: 9.7%
Mongolia | MNG | GDP deflator (base year varies by country) | NY.GDP.DEFL.ZS | 55.096 | 60.8527 | 64.7288 | 71.3549 | 83.265 | 100 | 121.9868 | 136.1721 | 165.3793 | 168.4003 | 202.1364 | 230.6377 | 251.1644 | 275.5274
Mongolia | MNG | GDP growth (annual %) | NY.GDP.MKTP.KD.ZG | 1.1461 | 2.9527 | 4.733 | 7.0046 | 10.6254 | 7.2537 | 8.5562 | 10.248 | 8.9004 | -1.2686 | 6.3652 | 10.3 | 7.6 | 22.9 | 15.7 | 9 | 15.5
Mongolia | MNG | GDP per capita (constant 2000 US$) | NY.GDP.PCAP.KD | 471.4733 | 480.7797 | 498.5509 | 527.8218 | 577.1045 | 610.9771 | 653.8075 | 709.7234 | 760.4425 | 738.5617 | 772.9331
Mongolia | MNG | GDP per capita (constant LCU) | NY.GDP.PCAP.KN | 921339.8137 | 939526.0855 | 974253.9744 | 1031454.3562 | 1127761.1789 | 1193954.0582 | 1277652.0312 | 1386921.403 | 1486035.1041 | 1443276.3296 | 1510443.8927
Mongolia | MNG | GDP per capita (current US$) | NY.GDP.PCAP.CD | 471.4733 | 520.8421 | 567.9704 | 641.925 | 792.2437 | 990.5866 | 1314.137 | 1613.5948 | 2108.0755 | 1690.417 | 2249.7659
Mongolia | MNG | GDP per capita growth (annual %) | NY.GDP.PCAP.KD.ZG | 0.20199 | 1.9739 | 3.6963 | 5.8712 | 9.337 | 5.8694 | 7.0102 | 8.5524 | 7.1463 | -2.8774 | 4.6538 | 7.5307
|  | Real GDP per capita growth, in % |  | 0.202% | 1.974% | 3.696% | 5.871% | 9.337% | 5.869% | 7.01% | 8.552% | 7.146% | -2.877% | 4.654% | 7.531%
|  | Index (2003 = 100) |  | 2003: 100; 2004: 109.337; 2005: 115.7544; Last Updated: 3/1/2013 2006: 123.869; Last Updated: 3/1/2013 2007: 134.4627; Last Updated: 3/1/2013 2008: 144.0718; Last Updated: 3/1/2013 2009: 139.9263; Last Updated: 3/1/2013 2010: 146.4383; Last Updated: 3/1/2013 2011: 157.4662
2003 economic prices used in SRV1 report. Use 2011 rGDP index above to convert values to real 2011 values.
Note on Q4: MCC: This year forward - IMF Art. IV. 2011.

## QDRP excerpt
QDRP Excerpt | [11 empty] | Last Updated: 3/1/2013
|  |  |  | 2012 |  |  |  | 2013 (thru Sep.)
Forecasted Cash for -> | Next Period |  |  |  | Projections for Future Quarters
| 14th Compact Quarter |  |  | 14th Compact Quarter | 15th Compact Quarter | 16th Compact Quarter | 17th Compact Quarter | 18th Compact Quarter | 19th Compact Quarter | 20th Compact Quarter
Date/Month/Quarter -> | 40909 | 40940 | 40969 | 40909 | 41000 | 41091 | 41183 | 41275 | 41365 | 41456
|  |  |  | 40969 | 41061 | 41153 | 41244 | 41334 | 41426 | 41518
| 2012001 | 2012002 | 2012003 | 2012001 | 2012004 | 2012007 | 2012010 | 2013001 | 2013004 | 2013007
| 2012001 | 2012002 | 2012003 | 2012003 | 2012006 | 2012009 | 2012012 | 2013003 | 2013006 | 2013009 |  |  | Program Admin Breakdown |  |  |  | Alloc amts of M&E & Pgm Admin ($ mln)
Column Number | Column 3 | Column 4 | Column 5 | Column 6 | Column 7 | Column 8 | Column 9 | Column 10 | Column 11 | Column 12 | Totals |  | Activity | Amount ($mln) | % | % Project funds
North South Road Project | [12 empty] | Rail | 0.4 | 0.1418% | 0.1617% | 0.056103
A- CHOIR-SAINSHAND ROAD ACT-TY | 0 | 6000000 | 0 | 6000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9797037.65 | 60797037.65 |  | Prop Rts | 27.1 | 9.607% | 10.95% | 3.801
A1-Choir Sainshand Road Activi |  | 6000000 |  | 6000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 60000000 |  | Voc Ed | 47.3 | 16.77% | 19.12% | 6.6342
A2 - Road construction - Bonus |  |  |  | 0 | [6 empty] | 0 |  | Health | 38.9 | 13.79% | 15.72% | 5.4561
A3 Road Construction -Continge |  |  |  | 0 | [6 empty] | 0 |  | Road | 88.4 | 31.34% | 35.73% | 12.3989
A4 - Refund Performance Guaran |  |  |  | 0 | [5 empty] | 797037.65 | 797037.65 |  | EEP | 45.3 | 16.06% | 18.31% | 6.3537
Bayanzurkh Bridge & Nalaikh Ro | 0 | 0 | 0 | 0 | 1702592 | 1702592 | 1702592 | 1702592 | 1702592 | 1702592 | 10215552 |  | M&E | 8.2 | 2.907%
B1 -Bridge & Road Construction |  |  |  | 0 | 1702592 | 1702592 | 1702592 | 1702592 | 1702592 | 1702592 | 10215552 |  | Program Admin | 26.5 | 9.394%
B2 - Refund Performance Guaran |  |  |  | 0 | [6 empty] | 0 |  | TOTAL | 282.1 | 100%
Project Maint and Supervision | 146800 | 27000 | 27000 | 200800 | 412019 | 612195.25 | 308176.25 | 108000 | 412019 | 805235.25 | 2447241.7348 |  | TOTAL Proj. funds | 247.4 |  | 100%
C1 Proj Mgt and Sup Consultant | 146800 | 27000 | 27000 | 200800 | 412019 | 612195.25 | 308176.25 | 108000 | 412019 | 689395.25 | 2348065.9566 |  | TOTAL M&E & Pgm Admin | 34.7 |  |  | 34.7
C2 - Project Mgt Contingency |  |  |  | 0 | [5 empty] | 115840 | 99175.7782
Road Maint Imp Tech Asst | 0 | 0 | 0 | 0 | 120000 | 120000 | 120000 | 150000 | 120000 | 120000 | 750000
D1-Road Maint Imp Tech Assista |  |  |  | 0 | 120000 | 120000 | 120000 | 150000 | 120000 | 120000 | 750000
Bridge Design and Nalaikh Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E1 /Bridge Design & Nalaikh Ro |  |  |  | 0 | [6 empty] | 0
Project Administration Costs | 78754.6 | 33754.6 | 33754.6 | 146263.8 | 98704.8 | 98705.8 | 98706.8 | 98707.8 | 98708.8 | 98707.95 | 904462.75
Salaries and Benefits | 19643.2 | 19643.2 | 19643.2 | 58929.6 | 58929.6 | 58929.6 | 58929.6 | 58929.6 | 58929.6 | 58929.6 | 412507.2
Communication | 178.4 | 178.4 | 178.4 | 535.2 | 535.2 | 535.2 | 535.2 | 535.2 | 535.2 | 535.35 | 3746.55
Office Operating Cost | 6031 | 6031 | 6031 | 18093 | 15534 | 15534 | 15534 | 15534 | 15534 | 15532 | 111295
Offic-Major Cap Assets |  |  |  | 0 | [6 empty] | 0
Small Furniture and Equipment |  |  |  | 0 | [6 empty] | 0
Travel | 4942 | 4942 | 4942 | 14826 | 14826 | 14827 | 14828 | 14829 | 14830 | 14831 | 103797
Travel International | 4942 | 4942 | 4942 | 14826 | 14826 | 14827 | 14828 | 14829 | 14830 | 14831 | 103797
Vehicle Rental |  |  |  | 0 | [6 empty] | 0
Vehicles O&M | 2960 | 2960 | 2960 | 8880 | 8880 | 8880 | 8880 | 8880 | 8880 | 8880 | 62160
Road Project Vehicle Fuel | 2960 | 2960 | 2960 | 8880 | 8880 | 8880 | 8880 | 8880 | 8880 | 8880 | 62160
Prof /Short Term Service | 45000 |  |  | 45000 | [6 empty] | 45000
Training/Seminar/workshop |  |  |  | 0 | [6 empty] | 0
[12 empty] | 1700000 | Budget reallocation from February 10, 2012
TOTAL North South Road Project | 225554.6 | 6060754.6 | 60754.6 | 6347063.8 | 11333315.8 | 11533493.05 | 11229475.05 | 11059299.8 | 11333319.8 | 12523572.85 | 76814294.1348
Compute project administration adder by deducting construction costs
Deduct budgeted construction cost because accounted for separately | [10 empty] | 60797037.65
Deduct Bayanzurkh & Nalaikh | [10 empty] | 10215552
Deduct Road Maint Imp Tech Asst | [10 empty] | 750000
Project-specific admin to allocate | [10 empty] | 5051704.4848
Note on B47: MCC: This line item is independent of Choir.
Note on M22: MCC: Reduced proportionately to B falling out.
Note on M23: MCC: Reduced proportionately to B falling out.

## CS Model
Mongolia |  |  |  | ERR: | 11.45% | (See cell M41 below for overall ERR accounting for IP and road non-completion) | [7 empty] | NB: Road was completed under the Compact
Analysis of the Choir-Sainshand Road
This file updates Mong_NS_Road_Oct09_IM_2_0.xls | [9 empty] | VOC savings |  | Time savings
This branch of file Mong_NS_Road_June2011_3_0.xls estimates returns for partial road completion. | [9 empty] | normal (USD/trip) |  | normal (USD/trip) |  |  | Bridge
Road Length (km) |  |  |  | CEU conversion |  | pass. Cars |  | Composition |  | Choir-ZU | Choir-Sain | Choir-ZU | Choir-Sain |  |  |  | 5600 | 1236483.1434 | 84624.9315 | 1321108.0749
Choir-Sainshand | 176 | 41.41% |  | car |  | 1 |  | 32% | 0.32 | 39.182 | 16.226 | 8.481 | 1.7561 |  | 0.3142 | 0.068008 | 1792
Sain.-ZU | 248 | 58.59% |  | jeep |  | 1 |  | 31% | 0.31 | 87.934 | 36.415 | 12.793 | 2.6489 |  | 0.70513 | 0.10259 | 1736
Choir-ZU (total) | 425 |  |  | light truck |  | 1.5 |  | 2% | 0.013333 | 116.875 | 48.4 | 2.519 | 0.52158 |  | 0.93721 | 0.0202 | 75
Update 2004-09 values |  | 10% |  | med truck |  | 2 |  | 19% | 0.095 | 176.572 | 73.1216 | 12.496 | 2.5874 |  | 1.4159 | 0.1002 | 532
annual maintenance (USD/km) |  | 5000 |  | heavy truck |  | 2.5 |  | 3% | 0.012 | 270.402 | 111.9782 | 28.182 | 5.8353 |  | 2.1683 | 0.22599 | 67
periodic maintenance (USD/km) |  | 0 |  | art. truck |  | 3 |  | 7% | 0.023333 | 389.796 | 161.4214 | 40.513 | 8.3886 |  | 3.1257 | 0.32487 | 131
interval for periodic maint. (y) |  | 7 |  | light bus |  | 1.275 |  | 5% | 0.039216 | 101.607 | 42.0773 | 21.34 | 4.4186 |  | 0.81477 | 0.17112 | 220
Capital Cost (USD/km) |  | 415203.7841 | 0.5 | bus |  | 1.7 |  | 1% | 0.0058824 | 162.228 | 67.1815 | 51.282 | 10.6184 |  | 1.3009 | 0.41122 | 33
benefit variation |  | 1 | 0.4 | heavy bus |  | 2.125 |  | 0% | 0 | 207.647 | 85.9903 | 163.46 | 33.8458 |  | 1.6651 | 1.3108
time discount |  | 0.5 |  | motorcycle |  | 0.5 |  | 0% | 0
Road integrity factor |  | 40%
Induced traffic variation |  | 1 |  | % of road completed with 2009 budget |  |  |  | 100% | 0.43189 | 0.23154 | 0.025571 | 0.030441
Normal traffic variation |  | 1 |  | (2009 Budget = USD 52.8 million)
Indus. park traffic variation |  | 1
Capital cost variation |  | 1
normal indus. park variation |  | 0.5
normal growth |  | 7% | [12 empty] | Lookup table
induced growth |  | 6% |  |  |  | Option of completion by GoM / another donor | [8 empty] | Lookup row | Fraction left uncompleted | # years over which supervision costs are spread
Transit share of benefits |  | 0.1 |  |  |  | 0 | Delay in benefits due to non-completion (0, 1, 2 or 4 years - see scenarios below) | [7 empty] | 0 | 0% | 0
Sensitivity analysis for risk of non-completion | [6 empty] | (Construction supervision costs also incurred for time of delay) | [7 empty] | 1 | 50% | 1
Scenarios | Probability | % completed |  |  |  | Corresp. ERR | Prob | Conditional prob | Scenario | [5 empty] | 2 | 54.17% | 2
Optimistic | 25% | 75% |  |  | 0 |  | 0% |  | Probability of completion by MCC | [5 empty] | 4 | 62.5% | 2
Likely | 50% | 50% |  |  |  |  | 100% |  | Probability of non-completion by MCC, of which
Pessimistic | 25% | 37.5% |  |  | 1 |  | 40% | 40% | Probability of completion by others within 1 year of compact close (delay of 1 year in benefits)
%Completion fraction by compact close (%) |  | 53.12% |  |  | 2 |  | 40% | 40% | Probability of completion by others not within 1 year, but within 2 years, of compact close (delay of 2 years in benefits)
Exponent for %Benefits(%Completion) relationship (Assume in the interval [0,3]) |  | 1.5 |  |  | 4 |  | 20% | 20% | Probability of completion by others not within 3 years, but within 4 years, of compact close (delay of 4 years in benefits)
%Benefits(%Completion) |  | 38.72% |  |  |  |  | Expected ERR across above scenarios
Exchange rate (MNT/USD) |  | 1370 | [5 empty] | Delay in benefits due to non-completion (see above)
Supervision costs as % of remaining capital cost |  | 5% |  |  |  |  | Prob(Delay in benefits) | 0% | 40% | 40% | 20%
Total supervision costs to allocate, post-compact ($ million) |  | 0 |  |  |  | Years delay for IP | ERR | 0 | 1 | 2 | 4 | Expectation (wrt delay in benefits)
# of years over which to allocate supervision costs |  | 0 |  |  |  | 0 | 16.49% | 15.28% | 14.88% | 14.2% | 12.57% | 14.15%
Supervision costs per year, for above # of years ($ million) |  | 0 |  |  |  | 1 | 15.27% | 14.15% | 13.77% | 13.17% | 11.68% | 13.11%
[6 empty] | 2 | 14.23% | 13.17% | 12.8% | 12.27% | 10.89% | 12.21%
[6 empty] | 3 | 13.32% | 12.31% | 11.96% | 11.47% | 10.16% | 11.4%
[6 empty] | No IP | 8.071% | 7.081% | 6.703% | 6.073% | 4.886% | 6.087%
[6 empty] | Expected ERR (wrt IP development) | 11.45% | 10.4% | 10.03% | 9.425% | 8.105% | 9.402% | Overall Expected ERR
Sainshand-ZU without project development
Feasibility Study projection after adjustment for road completion
|  | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
| Normal | 192 | 205 | 219 | 234 | 250 | 267 | 285 | 304 | 325 | 347 | 371 | 396 | 424 | 454 | 486 | 520 | 556 | 595 | 637 | 682 | 730 | 781
| Induced |  |  |  |  | 277 | 292 | 311 | 330 | 350 | 371 | 393 | 416 | 441 | 467 | 495 | 525 | 557 | 590 | 625 | 663 | 703 | 745
| Generated | 15 | 16 | 17 | 18 | 19 | 21 | 22 | 23 | 25 | 27 | 29 | 30 | 33 | 35 | 37 | 40 | 42 | 45 | 48 | 52 | 55 | 58
Diverted
| Total | 207 | 221 | 236 | 252 | 546 | 580 | 618 | 657 | 700 | 745 | 793 | 842 | 898 | 956 | 1018 | 1085 | 1155 | 1230 | 1310 | 1397 | 1488 | 1584
Government revised projection
|  | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
| Normal | 93 | 99 | 105 | 112 | 119 | 126 | 134 | 143 | 152 | 162 | 173 | 184 | 196 | 208 | 222 | 236 | 252 | 270 | 289 | 309 | 331 | 354
| Induced |  |  |  |  | 1094 | 1201 | 1530 | 1861 | 1933 | 1997 | 2064 | 2136 | 2201 | 2266 | 2885 | 2960 | 3039 | 3130 | 3224 | 3321 | 3421 | 3524
| Generated? |  |  |  |  | 100 | 100 | 100 | 100 | 200 | 200 | 200 | 200 | 200 | 200 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 301
| Diverted? |  |  |  |  | 26 | 27 | 29 | 31 | 33 | 35 | 38 | 40 | 43 | 45 | 48 | 51 | 55 | 58 | 62 | 66 | 75 | 85.2273
| Total | 93 | 99 | 105 | 112 | 1339 | 1454 | 1793 | 2135 | 2318 | 2394 | 2475 | 2560 | 2640 | 2719 | 3455 | 3547 | 3646 | 3758 | 3875 | 3996 | 4127 | 4264.2273
[7 empty] | 0.085885 | 0.23315 | 0.19074 | 0.085714 | 0.032787 | 0.033835 | 0.034343 | 0.03125 | 0.029924 | 0.27069 | 0.026628 | 0.027911 | 0.030719 | 0.031134 | 0.031226 | 0.032783 | 0.033251
Estimated variance/expected impact of Sainshand Industrial Estate
|  | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
| Normal | -99 | -106 | -114 | -122 | -131 | -141 | -151 | -161 | -173 | -185 | -198 | -212 | -228 | -246 | -264 | -284 | -304 | -325 | -348 | -373 | -399 | -427
| Induced | 0 | 0 | 0 | 0 | 817 | 909 | 1219 | 1531 | 1583 | 1626 | 1671 | 1720 | 1760 | 1799 | 2390 | 2435 | 2482 | 2540 | 2599 | 2658 | 2718 | 2779
| Generated? | -15 | -16 | -17 | -18 | 81 | 79 | 78 | 77 | 175 | 173 | 171 | 170 | 167 | 165 | 263 | 260 | 258 | 255 | 252 | 248 | 245 | 243
| Diverted? | 0 | 0 | 0 | 0 | 26 | 27 | 29 | 31 | 33 | 35 | 38 | 40 | 43 | 45 | 48 | 51 | 55 | 58 | 62 | 66 | 75 | 85.2273
| Total | -114 | -122 | -131 | -140 | 793 | 874 | 1175 | 1478 | 1618 | 1649 | 1682 | 1718 | 1742 | 1763 | 2437 | 2462 | 2491 | 2528 | 2565 | 2599 | 2639 | 2680.2273
Estimated traffic projections (occuring in the absence of investment in the Choir Sainshand road)
|  | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
| Normal | 93 | 99 | 105 | 112 | 119 | 126 | 134 | 143 | 152 | 162 | 173 | 184 | 196 | 208 | 222 | 236 | 252 | 270 | 289 | 309 | 331 | 354
| Induced |  |  |  |  | 132 | 138 | 146 | 155 | 164 | 173 | 183 | 193 | 204 | 214 | 226 | 238 | 252 | 268 | 284 | 300 | 319 | 338
| Industrial Park |  |  |  |  | 962 | 1063 | 1384 | 1706 | 1769 | 1824 | 1881 | 1943 | 1997 | 2052 | 2659 | 2722 | 2787 | 2862 | 2940 | 3021 | 3102 | 3186
| Generated |  |  |  |  | 100 | 100 | 100 | 100 | 200 | 200 | 200 | 200 | 200 | 200 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 301
| Diverted |  |  |  |  | 26 | 27 | 29 | 31 | 33 | 35 | 38 | 40 | 43 | 45 | 48 | 51 | 55 | 58 | 62 | 66 | 75 | 85.2273
| Total |  |  |  |  | 1339 | 1454 | 1793 | 2135 | 2318 | 2394 | 2475 | 2560 | 2640 | 2719 | 3455 | 3547 | 3646 | 3758 | 3875 | 3996 | 4127 | 4264.2273
Choir-Sainshand without project
Adjusted feasibility study projections
|  | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
| Normal | 149 | 156 | 142 | 149 | 156 | 163 | 171 | 179 | 187 | 196 | 205 | 215 | 225 | 236 | 247 | 259 | 271 | 284 | 298 | 312 | 328 | 344
| Induced |  |  |  |  | 541 | 567 | 605 | 639 | 675 | 712 | 750 | 790 | 846 | 889 | 934 | 981 | 1015 | 1048 | 1084 | 1121 | 1161 | 1162
Industrial Park
Diverted
| Generated |  |  |  |  | 15 | 16 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 30 | 31 | 32
| Total | 149 | 156 | 142 | 149 | 712 | 746 | 792 | 835 | 880 | 927 | 975 | 1026 | 1093 | 1148 | 1205 | 1265 | 1312 | 1359 | 1410 | 1463 | 1520 | 1538
[6 empty] | 0.04698 | 0.044872 | 0.04908 | 0.046784 | 0.044693 | 0.048128 | 0.045918 | 0.04878 | 0.046512 | 0.048889 | 0.04661 | 0.048583 | 0.046332 | 0.04797 | 0.049296 | 0.04698 | 0.051282 | 0.04878
Revised Govt projections Choir without Sainshand segment
|  | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
| Normal | 127 | 135 | 143 | 152 | 161 | 171 | 182 | 194 | 206 | 219 | 233 | 248 | 264 | 281 | 299 | 318 | 339 | 361 | 384 | 409 | 436 | 464.7824
| Induced |  |  |  |  | 949 | 1260 | 1572 | 2160 | 2216 | 2259 | 2304 | 2351 | 2385 | 2418 | 3276 | 3313 | 3353 | 3393 | 3433 | 3473 | 3513 | 3553.4607
Industrial Park
| Diverted |  |  |  |  | 35 | 37 | 39 | 41 | 44 | 47 | 50 | 53 | 56 | 60 | 64 | 68 | 72 | 77 | 82 | 87 | 99 | 112.6552
| Generated |  |  |  |  | 100 | 100 | 100 | 100 | 200 | 200 | 200 | 200 | 200 | 200 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300
| Total | 127 | 135 | 143 | 152 | 1245 | 1568 | 1893 | 2495 | 2666 | 2725 | 2787 | 2852 | 2905 | 2959 | 3939 | 3999 | 4064 | 4131 | 4199 | 4269 | 4348 | 4430.8983
|  |  | 0.062992 | 0.059259 | 0.062937 | 0.059211 | 0.062112 | 0.064327 | 0.065934 | 0.061856 | 0.063107 | 0.063927 | 0.064378 | 0.064516 | 0.064394 | 0.064057 | 0.063545 | 0.066038 | 0.064897 | 0.063712 | 0.065104 | 0.066015 | 0.066015
[7 empty] | 0.32771 | 0.24762 | 0.37405 | 0.025926 | 0.019404 | 0.01992 | 0.020399 | 0.014462 | 0.013836 | 0.35484 | 0.011294 | 0.012074 | 0.01193 | 0.011789 | 0.011652 | 0.011517 | 0.011517
| Variance | 2023: 2451.4566; 2024: 2485.3761; 2025: 2519.765; 2026: 2554.6297; 2027: 2589.9767; 2028: 2625.8129; 2029: 2662.1449; 2030: 2698.9796
|  | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
| Normal | -22 | -21 | 1 | 3 | 5 | 8 | 11 | 15 | 19 | 23 | 28 | 33 | 39 | 45 | 52 | 59 | 68 | 77 | 86 | 97 | 108 | 120.7824
| Induced | 0 | 0 | 0 | 0 | 408 | 693 | 967 | 1521 | 1541 | 1547 | 1554 | 1561 | 1539 | 1529 | 2342 | 2332 | 2338 | 2345 | 2349 | 2352 | 2352 | 2391.4607
| Industrial Park | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Diverted | 0 | 0 | 0 | 0 | 35 | 37 | 39 | 41 | 44 | 47 | 50 | 53 | 56 | 60 | 64 | 68 | 72 | 77 | 82 | 87 | 99 | 112.6552
| Generated | 0 | 0 | 0 | 0 | 85 | 84 | 84 | 83 | 182 | 181 | 180 | 179 | 178 | 177 | 276 | 275 | 274 | 273 | 272 | 270 | 269 | 268
| Total | -22 | -21 | 1 | 3 | 533 | 822 | 1101 | 1660 | 1786 | 1798 | 1812 | 1826 | 1812 | 1811 | 2734 | 2734 | 2752 | 2772 | 2789 | 2806 | 2828 | 2892.8983
| Revised Induced Traffic Series with Completion of Works in 2013 |  |  |  |  | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
| Traffic |  |  |  |  | 0 | 949 | 1260 | 1572 | 2160 | 2216 | 2259 | 2304 | 2351 | 2385 | 2418 | 3276 | 3313 | 3353 | 3393 | 3433 | 3473 | 3513
| Estimated traffic projections (occuring in the absence of investment in the Sainshand ZU road) |  |  |  |  | 2016: NB: Adjusted to account for completion of works in 2013)
|  | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
| Normal | 127 | 135 | 143 | 152 | 161 | 171 | 182 | 194 | 206 | 219 | 233 | 248 | 264 | 281 | 299 | 318 | 339 | 361 | 384 | 409 | 436 | 464.7824
| Induced |  |  |  |  | 0 | 593 | 633 | 686 | 735 | 791 | 846 | 907 | 970 | 1057 | 1126 | 1202 | 1284 | 1352 | 1417 | 1488 | 1567 | 1645
| Industrial Park |  |  |  |  | 0 | 0 | 0 | 886 | 1425 | 1425 | 1413 | 1397 | 1381 | 1328 | 1292 | 2074 | 2029 | 2001 | 1976 | 1945 | 1906 | 1868
| Diverted |  |  |  |  | 0 | 35 | 37 | 39 | 41 | 44 | 47 | 50 | 53 | 56 | 60 | 64 | 68 | 72 | 77 | 82 | 87 | 99
| Generated |  |  |  |  | 0 | 100 | 100 | 100 | 100 | 200 | 200 | 200 | 200 | 200 | 200 | 300 | 300 | 300 | 300 | 300 | 300 | 300
| Total |  |  |  |  | 161 | 899 | 952 | 1905 | 2507 | 2679 | 2739 | 2802 | 2868 | 2922 | 2977 | 3958 | 4020 | 4086 | 4154 | 4224 | 4296 | 4376.7824
|  | 764 | -0.98757
9.5
Working Hypoth Choir-Sainshand without project given Sainshand-ZU - Industrial Park completed in 2012
|  | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
| Normal | 127 | 135 | 143 | 152 | 161 | 171 | 182 | 194 | 206 | 219 | 233 | 248 | 264 | 281 | 299 | 318 | 339 | 361 | 384 | 409 | 436 | 464.7824
| Normal Indus Park |  |  |  |  | 0 | 0 | 0 | 443 | 713 | 713 | 707 | 699 | 691 | 664 | 646 | 1037 | 1015 | 1001 | 988 | 973 | 953 | 934
| Total |  |  |  |  | 161 | 171 | 182 | 637 | 919 | 932 | 940 | 947 | 955 | 945 | 945 | 1355 | 1354 | 1362 | 1372 | 1382 | 1389 | 1398.7824
Vehicle Composition (normal traffic)
car | 32% |  |  |  |  | 52 | 55 | 58 | 204 | 294 | 298 | 301 | 303 | 306 | 302 | 302 | 434 | 433 | 436 | 439 | 442 | 444 | 448
jeep | 31% |  |  |  |  | 50 | 53 | 56 | 197 | 285 | 289 | 291 | 294 | 296 | 293 | 293 | 420 | 420 | 422 | 425 | 428 | 431 | 434
light truck | 2% |  |  |  |  | 2 | 2 | 2 | 8 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 18 | 18 | 18 | 18 | 18 | 19 | 19
med truck | 19% |  |  |  |  | 15 | 16 | 17 | 61 | 87 | 89 | 89 | 90 | 91 | 90 | 90 | 129 | 129 | 129 | 130 | 131 | 132 | 133
heavy truck | 3% |  |  |  |  | 2 | 2 | 2 | 8 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 16 | 16 | 16 | 16 | 17 | 17 | 17
art. truck | 7% |  |  |  |  | 4 | 4 | 4 | 15 | 21 | 22 | 22 | 22 | 22 | 22 | 22 | 32 | 32 | 32 | 32 | 32 | 32 | 33
light bus | 5% |  |  |  |  | 6 | 7 | 7 | 25 | 36 | 37 | 37 | 37 | 37 | 37 | 37 | 53 | 53 | 53 | 54 | 54 | 54 | 55
bus | 1% |  |  |  |  | 1 | 1 | 1 | 4 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8
heavy bus | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Working Hypoth Choir-Sainshand with project given Sainshand-ZU - Industrial Park completed in 2015 |  | 2016: (NB assumes higher induced volume than completion of Choir-Sainshand without building of Sainshand-ZU)
| Project Year |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
| Calendar Year | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
| Normal |  |  |  |  | 161 | 171 | 182 | 637 | 919 | 932 | 940 | 947 | 955 | 945 | 945 | 1355 | 1354 | 1362 | 1372 | 1382 | 1389 | 1398.7824
| Induced |  |  |  |  | 0 | 830 | 886 | 960 | 1029 | 1107 | 1184 | 1270 | 1358 | 1480 | 1576 | 1683 | 1798 | 1893 | 1984 | 2083 | 2194 | 2303
| Induced Indus Park |  |  |  |  | 0 | 0 | 0 | 443 | 712 | 712 | 706 | 698 | 690 | 664 | 646 | 1037 | 1014 | 1000 | 988 | 972 | 953 | 934
| Diverted |  |  |  |  | 0 | 35 | 37 | 39 | 41 | 44 | 47 | 50 | 53 | 56 | 60 | 64 | 68 | 72 | 77 | 82 | 87 | 99
| Generated |  |  |  |  | 0 | 100 | 100 | 100 | 100 | 200 | 200 | 200 | 200 | 200 | 200 | 300 | 300 | 300 | 300 | 300 | 300 | 300
| Total |  |  |  |  | 161 | 1136 | 1205 | 2179 | 2801 | 2995 | 3077 | 3165 | 3256 | 3345 | 3427 | 4439 | 4534 | 4627 | 4721 | 4819 | 4923 | 5034.7824 | 118117.65 | 833426.4 | 884048.25 | 1598623.35 | 2054953.65 | 2197281.75 | 2257441.05 | 2322002.25 | 2388764.4 | 2454059.25 | 2514218.55 | 3256672.35 | 3326369.1 | 3394598.55 | 3463561.65 | 3535459.35 | 3611758.95
|  | 4 2013: 0; 5 2014: 6.0559; 6 2015: 0.060739; (NB assumes higher induced volume than completion of Choir-Sainshand without building of Sainshand-ZU) 7 2016: 0.8083; (NB assumes higher induced volume than completion of Choir-Sainshand without building of Sainshand-ZU) 8 2017: 0.28545; (NB assumes higher induced volume than completion of Choir-Sainshand without building of Sainshand-ZU) 9 2018: 0.069261; (NB assumes higher induced volume than completion of Choir-Sainshand without building of Sainshand-ZU) 10 2019: 0.027379; (NB assumes higher induced volume than completion of Choir-Sainshand without building of Sainshand-ZU) 11 2020: 0.028599; (NB assumes higher induced volume than completion of Choir-Sainshand without building of Sainshand-ZU) 12 2021: 0.028752 | 2746.9221 | 19382.0093 | 20559.2616 | 37177.2872 | 47789.6198 | 51099.5756 | 52498.6291 | 54000.0523 | 55552.6605 | 57071.1453 | 58470.1988 | 75736.5663 | 77357.4209 | 78944.1523 | 80547.9453 | 82219.9849 | 83994.3942
NB: The base spreadsheet double counted normal traffic
Vehicle Composition (induced/generated/diverted traffic)
car | 32% |  |  |  |  | 0 | 309 | 327 | 493 | 602 | 660 | 684 | 710 | 736 | 768 | 794 | 987 | 1018 | 1045 | 1072 | 1100 | 1131 | 1164
jeep | 31% |  |  |  |  | 0 | 299 | 317 | 478 | 583 | 640 | 662 | 688 | 713 | 744 | 769 | 956 | 986 | 1012 | 1038 | 1065 | 1096 | 1127
light truck | 2% |  |  |  |  | 0 | 13 | 14 | 21 | 25 | 28 | 28 | 30 | 31 | 32 | 33 | 41 | 42 | 44 | 45 | 46 | 47 | 48
med truck | 19% |  |  |  |  | 0 | 92 | 97 | 146 | 179 | 196 | 203 | 211 | 219 | 228 | 236 | 293 | 302 | 310 | 318 | 327 | 336 | 345
heavy truck | 3% |  |  |  |  | 0 | 12 | 12 | 19 | 23 | 25 | 26 | 27 | 28 | 29 | 30 | 37 | 38 | 39 | 40 | 41 | 42 | 44
art. truck | 7% |  |  |  |  | 0 | 23 | 24 | 36 | 44 | 48 | 50 | 52 | 54 | 56 | 58 | 72 | 74 | 76 | 78 | 80 | 82 | 85
light bus | 5% |  |  |  |  | 0 | 38 | 40 | 60 | 74 | 81 | 84 | 87 | 90 | 94 | 97 | 121 | 125 | 128 | 131 | 135 | 139 | 143
bus | 1% |  |  |  |  | 0 | 6 | 6 | 9 | 11 | 12 | 13 | 13 | 14 | 14 | 15 | 18 | 19 | 19 | 20 | 20 | 21 | 21
heavy bus | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Estimated benefits (USD million) |  |  |  |  | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
VOC savings normal traffic | [5 empty] | 1658074.7276 | 1747795.2289 | 1823693.3529 | 6559906.8846 | 9383073.1837 | 9567133.6166 | 9645017.4822 | 9715585.3791 | 9779521.1687 | 9698292.8176 | 9698292.8176 | 13916883.2383 | 13911553.0112 | 13951468.3614 | 14041188.8626 | 14153871.8385 | 14240339.1355 | 14388416.7945
Time savings normal traffic | [5 empty] | 113651.1558 | 120293.7381 | 125484.7987 | 449232.4966 | 642248.968 | 653944.1925 | 661074.6058 | 665688.7987 | 670009.6945 | 664241.7663 | 664241.7663 | 952246.1166 | 951669.249 | 955140.1815 | 961782.7638 | 968890.7308 | 973676.2632 | 983651.3597
VOC savings induced/generated/diverted traffic | [5 empty] | 0 | 4979526.7262 | 5243496.4212 | 7911257.8695 | 9662417.0373 | 10588194.581 | 10971002.0031 | 11399939.3833 | 11825980.4539 | 12311786.0597 | 12737827.1303 | 15817760.135 | 16305954.0178 | 16737556.5114 | 17172243.8628 | 17623464.3456 | 18117639.3956 | 18651016.0062
Time savings induced/generated/diverted traffic | [5 empty] | 0 | 340662.4149 | 358725.6297 | 541068.1792 | 661063.3827 | 724326.5341 | 751431.083 | 779705.0796 | 809202.3947 | 842447.4789 | 871944.794 | 1082531.4117 | 1116797.0504 | 1145359.4808 | 1175580.3121 | 1205931.3314 | 1240632.0525 | 1276501.8471
[6 empty] | 1771725.8834 | 7188278.1081 | 7551400.2025 | 15461465.43 | 20348802.5717 | 21533598.9242 | 22028525.1741 | 22560918.6407 | 23084713.7117 | 23516768.1225 | 23972306.5082 | 31769420.9016 | 32285973.3283 | 32789524.5351 | 33350795.8013 | 33952158.2464 | 34572286.8468 | 35299586.0075
annual maintenance | [5 empty] | 880000 | 880000 | 880000 | 880000 | 889206.3492 | 950793.6508 | 976825.3968 | 1004761.9048 | 1033650.7937 | 1061904.7619 | 1087936.5079 | 1409206.3492 | 1439365.0794 | 1468888.8889 | 1498730.1587 | 1529841.2698 | 1562857.1429 | 1598343.6178
periodic maintenance | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Additional supervision costs in the event of non-completion | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Basic investment |  |  |  | 32.7964 | 2012: 32.0376
Compact Management/Admin |  |  |  | 7.6538 | 2012: 7.4767
Incremental Net Benefits |  |  |  | -40.4502 | -39.5143 | 0.89173 | 6.3083 | 6.6714 | 14.5815 | 19.4596 | 20.5828 | 21.0517 | 21.5562 | 22.0511 | 22.4549 | 22.8844 | 30.3602 | 30.8466 | 31.3206 | 31.8521 | 32.4223 | 33.0094 | 33.7012
| ERR | 16.49%
Incremental Benefits |  |  |  | 0 | 0 | 891725.8834 | 6308278.1081 | 6671400.2025 | 14581465.43 | 19459596.2225 | 20582805.2734 | 21051699.7773 | 21556156.7359 | 22051062.9181 | 22454863.3606 | 22884370.0002 | 30360214.5524 | 30846608.249 | 31320635.6462 | 31852065.6426 | 32422316.9765 | 33009429.7039 | 33701242.3897
NPV Benefits @ 10% |  | 154334514.2105
Delay in Industrial Park operation 1 year
(USD million) | [5 empty] | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
Road User Benefits | [5 empty] | 1771725.8834 | 1868088.9669 | 7269367.2927 | 12611361.4322 | 18477648.2004 | 20544558.2291 | 21618613.2031 | 22103707.264 | 22629175.326 | 22997717.4324 | 23516768.1225 | 28478901.2792 | 31763513.8069 | 32329359.6111 | 32885887.6186 | 33470586.7443 | 34043411.0757 | 34730339.6023
Costs |  |  |  | 40.4502 | 39.5143 | 880000 | 880000 | 880000 | 880000 | 889206.3492 | 950793.6508 | 976825.3968 | 1004761.9048 | 1033650.7937 | 1061904.7619 | 1087936.5079 | 1409206.3492 | 1439365.0794 | 1468888.8889 | 1498730.1587 | 1529841.2698 | 1562857.1429 | 1598343.6178
Incremental Net Benefits |  |  |  | -40.4502 | -39.5143 | 0.89173 | 0.98809 | 6.3894 | 11.7314 | 17.5884 | 19.5938 | 20.6418 | 21.0989 | 21.5955 | 21.9358 | 22.4288 | 27.0697 | 30.3241 | 30.8605 | 31.3872 | 31.9407 | 32.4806 | 33.132
| ERR | 15.27%
Incremental Benefits |  |  |  | 0 | 0 | 891725.8834 | 988088.9669 | 6389367.2927 | 11731361.4322 | 17588441.8512 | 19593764.5783 | 20641787.8063 | 21098945.3592 | 21595524.5324 | 21935812.6705 | 22428831.6145 | 27069694.93 | 30324148.7275 | 30860470.7222 | 31387157.4599 | 31940745.4744 | 32480553.9328 | 33131995.9845
NPV Benefits @ 10% |  | 143338273.4364
Delay in Industrial Park operation 2 years
(USD million) | [5 empty] | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
Road User Benefits | [5 empty] | 1771725.8834 | 1868088.9669 | 1949178.1516 | 12329328.5224 | 15627544.2026 | 18673403.8578 | 20629572.508 | 21693795.293 | 22171963.9494 | 22542179.0467 | 22997717.4324 | 28023362.8935 | 28472994.1845 | 31806900.0896 | 32425722.6946 | 33005678.5616 | 33561839.5736 | 34201463.8312
Costs |  |  |  | 40.4502 | 39.5143 | 880000 | 880000 | 880000 | 880000 | 889206.3492 | 950793.6508 | 976825.3968 | 1004761.9048 | 1033650.7937 | 1061904.7619 | 1087936.5079 | 1409206.3492 | 1439365.0794 | 1468888.8889 | 1498730.1587 | 1529841.2698 | 1562857.1429 | 1598343.6178
Incremental Net Benefits |  |  |  | -40.4502 | -39.5143 | 0.89173 | 0.98809 | 1.0692 | 11.4493 | 14.7383 | 17.7226 | 19.6527 | 20.689 | 21.1383 | 21.4803 | 21.9098 | 26.6142 | 27.0336 | 30.338 | 30.927 | 31.4758 | 31.999 | 32.6031
| ERR | 14.23%
Incremental Benefits |  |  |  | 0 | 0 | 891725.8834 | 988088.9669 | 1069178.1516 | 11449328.5224 | 14738337.8534 | 17722610.207 | 19652747.1111 | 20689033.3882 | 21138313.1557 | 21480274.2848 | 21909780.9244 | 26614156.5443 | 27033629.1051 | 30338011.2007 | 30926992.5359 | 31475837.2917 | 31998982.4307 | 32603120.2134
NPV Benefits @ 10% |  | 133434767.2506
Delay in Industrial Park operation 3 years
(USD million) | [5 empty] | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
Road User Benefits | [5 empty] | 1771725.8834 | 1868088.9669 | 1949178.1516 | 7009139.3813 | 15345511.2928 | 15823299.86 | 18758418.1367 | 20704754.5978 | 21762051.9783 | 22084967.67 | 22542179.0467 | 27504312.2034 | 28017455.7988 | 28516380.4672 | 31903263.1731 | 32545513.6375 | 33096931.3909 | 33719892.3291
Costs |  |  |  | 40.4502 | 39.5143 | 880000 | 880000 | 880000 | 880000 | 889206.3492 | 950793.6508 | 976825.3968 | 1004761.9048 | 1033650.7937 | 1061904.7619 | 1087936.5079 | 1409206.3492 | 1439365.0794 | 1468888.8889 | 1498730.1587 | 1529841.2698 | 1562857.1429 | 1598343.6178
Incremental Net Benefits |  |  |  | -40.4502 | -39.5143 | 0.89173 | 0.98809 | 1.0692 | 6.1291 | 14.4563 | 14.8725 | 17.7816 | 19.7 | 20.7284 | 21.0231 | 21.4542 | 26.0951 | 26.5781 | 27.0475 | 30.4045 | 31.0157 | 31.5341 | 32.1215
| ERR | 13.32%
Incremental Benefits |  |  |  | 0 | 0 | 891725.8834 | 988088.9669 | 1069178.1516 | 6129139.3813 | 14456304.9436 | 14872506.2093 | 17781592.7399 | 19699992.6931 | 20728401.1847 | 21023062.9081 | 21454242.5388 | 26095105.8542 | 26578090.7194 | 27047491.5783 | 30404533.0144 | 31015672.3677 | 31534074.248 | 32121548.7113
NPV Benefits @ 10% |  | 124518055.2236
NPV benefits in 2005 PPP USD |  | 117233185.1014 | 0.9415
Working Hypoth Choir-Sainshand without project given Sainshand-ZU - Industrial Park absent
|  | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
| Normal |  |  |  |  | 161 | 171 | 182 | 194 | 206 | 219 | 233 | 248 | 264 | 281 | 299 | 318 | 339 | 361 | 384 | 409 | 436 | 465
Normal Indus Park
| Total |  |  |  |  | 161 | 171 | 182 | 194 | 206 | 219 | 233 | 248 | 264 | 281 | 299 | 318 | 339 | 361 | 384 | 409 | 436 | 465
Vehicle Composition (normal traffic)
car | 32% |  |  |  |  | 52 | 55 | 58 | 62 | 66 | 70 | 75 | 79 | 84 | 90 | 96 | 102 | 108 | 116 | 123 | 131 | 140 | 149
jeep | 31% |  |  |  |  | 50 | 53 | 56 | 60 | 64 | 68 | 72 | 77 | 82 | 87 | 93 | 99 | 105 | 112 | 119 | 127 | 135 | 144
light truck | 2% |  |  |  |  | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6
med truck | 19% |  |  |  |  | 15 | 16 | 17 | 18 | 20 | 21 | 22 | 24 | 25 | 27 | 28 | 30 | 32 | 34 | 36 | 39 | 41 | 44
heavy truck | 3% |  |  |  |  | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 6
art. truck | 7% |  |  |  |  | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 9 | 10 | 10 | 11
light bus | 5% |  |  |  |  | 6 | 7 | 7 | 8 | 8 | 9 | 9 | 10 | 10 | 11 | 12 | 12 | 13 | 14 | 15 | 16 | 17 | 18
bus | 1% |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3
heavy bus | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Working Hypoth Choir-Sainshand with project given Sainshand-ZU - Industrial Park absent
|  | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
| Normal |  |  |  |  | 161 | 171 | 182 | 194 | 206 | 219 | 233 | 248 | 264 | 281 | 299 | 318 | 339 | 361 | 384 | 409 | 436 | 465
| Induced |  |  |  |  | 0 | 830 | 886 | 960 | 1029 | 1107 | 1184 | 1270 | 1358 | 1480 | 1576 | 1683 | 1798 | 1893 | 1984 | 2083 | 2194 | 2303
Induced Indus Park | bar: 2013
| Diverted |  |  |  |  | 0 | 35 | 37 | 39 | 41 | 44 | 47 | 50 | 53 | 56 | 60 | 64 | 68 | 72 | 77 | 82 | 87 | 99
| Generated |  |  |  |  | 19 | 21 | 22 | 23 | 25 | 27 | 29 | 30 | 33 | 35 | 37 | 40 | 42 | 45 | 48 | 52 | 55 | 58 | 361.8
| Total |  |  |  |  | 180 | 1057 | 1127 | 1216 | 1301 | 1397 | 1493 | 1598 | 1708 | 1852 | 1972 | 2105 | 2247 | 2371 | 2493 | 2626 | 2772 | 2925 | 132057 | 775468.05 | 826823.55 | 892118.4 | 954478.65 | 1024909.05 | 1095339.45 | 1172372.7 | 1253074.2 | 1358719.8 | 1446757.8 | 1544333.25 | 1648511.55 | 1739484.15 | 1828989.45 | 1926564.9 | 2033677.8
[5 empty] | 19 | -532 | 4.8722 | 0.066225 | 0.078971 | 0.069901 | 0.073789 | 0.068719 | 0.070328 | 0.068836 | 0.084309 | 0.064795 | 0.067444 | 0.067458 | 0.055185 | 0.051455 | 0.053349 | 0.055598 | 0.055195 | 3071.093 | 18034.1407 | 19228.4547 | 20746.9395 | 22197.1779 | 23835.0942 | 25473.0105 | 27264.4814 | 29141.2605 | 31598.1349 | 33645.5302 | 35914.7267 | 38337.4779 | 40453.1198 | 42534.6384 | 44803.8349 | 47294.8326
| Vehicle Composition (normal traffic) |  |  |  |  | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | Passengers
car | 32% |  |  |  |  | 52 | 55 | 58 | 62 | 66 | 70 | 75 | 79 | 84 | 90 | 96 | 102 | 108 | 116 | 123 | 131 | 140 | 149 | 3
jeep | 31% |  |  |  |  | 50 | 53 | 56 | 60 | 64 | 68 | 72 | 77 | 82 | 87 | 93 | 99 | 105 | 112 | 119 | 127 | 135 | 144
light truck | 2% |  |  |  |  | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6
med truck | 19% |  |  |  |  | 15 | 16 | 17 | 18 | 20 | 21 | 22 | 24 | 25 | 27 | 28 | 30 | 32 | 34 | 36 | 39 | 41 | 44
heavy truck | 3% |  |  |  |  | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 6
art. truck | 7% |  |  |  |  | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 9 | 10 | 10 | 11
light bus | 5% |  |  |  |  | 6 | 7 | 7 | 8 | 8 | 9 | 9 | 10 | 10 | 11 | 12 | 12 | 13 | 14 | 15 | 16 | 17 | 18
bus | 1% |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3
heavy bus | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Vehicle Composition (induced/generated/diverted traffic) |  |  |  |  | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
car | 32% |  |  |  |  | 6 | 284 | 302 | 327 | 350 | 377 | 403 | 432 | 462 | 503 | 535 | 572 | 611 | 643 | 675 | 709 | 748 | 787
jeep | 31% |  |  |  |  | 6 | 275 | 293 | 317 | 339 | 365 | 391 | 419 | 448 | 487 | 519 | 554 | 591 | 623 | 654 | 687 | 724 | 763
light truck | 2% |  |  |  |  | 0 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 21 | 22 | 24 | 25 | 27 | 28 | 30 | 31 | 33
med truck | 19% |  |  |  |  | 2 | 84 | 90 | 97 | 104 | 112 | 120 | 128 | 137 | 149 | 159 | 170 | 181 | 191 | 200 | 211 | 222 | 234
heavy truck | 3% |  |  |  |  | 0 | 11 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 19 | 20 | 21 | 23 | 24 | 25 | 27 | 28 | 30
art. truck | 7% |  |  |  |  | 0 | 21 | 22 | 24 | 26 | 27 | 29 | 32 | 34 | 37 | 39 | 42 | 45 | 47 | 49 | 52 | 55 | 57
light bus | 5% |  |  |  |  | 1 | 35 | 37 | 40 | 43 | 46 | 49 | 53 | 57 | 62 | 66 | 70 | 75 | 79 | 83 | 87 | 92 | 96
bus | 1% |  |  |  |  | 0 | 5 | 6 | 6 | 6 | 7 | 7 | 8 | 8 | 9 | 10 | 11 | 11 | 12 | 12 | 13 | 14 | 14
heavy bus | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Estimated benefits (USD million) | [5 empty] | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
VOC savings normal traffic | [5 empty] | 1658074.7276 | 1747795.2289 | 1823693.3529 | 1999632.7464 | 2116843.8714 | 2260641.786 | 2359162.6987 | 2555185.466 | 2703637.2286 | 2910320.4501 | 3088703.4878 | 3240499.7359 | 3475044.6919 | 3663286.1058 | 3936009.0752 | 4213260.1936 | 4456762.6845 | 4788091.2164
Time savings normal traffic | [5 empty] | 113651.1558 | 120293.7381 | 125484.7987 | 136501.3994 | 143989.4556 | 153995.9768 | 161210.9375 | 173776.3269 | 185520.9331 | 199240.0577 | 212140.6438 | 222522.765 | 237283.3938 | 251140.9367 | 269094.1651 | 287427.4827 | 306391.5388 | 328088.7953
VOC savings induced/generated/diverted traffic | [5 empty] | 82809.3126 | 4562131.9364 | 4849146.4088 | 5243496.4212 | 5620553.8721 | 6028727.7581 | 6449715.4383 | 6935120.0051 | 7403633.0494 | 8068106.0117 | 8582937.5622 | 9175511.5671 | 9791697.4904 | 10314478.7409 | 10800284.3467 | 11391293.1025 | 12000121.1576 | 12614804.6811
Time savings induced/generated/diverted traffic | [5 empty] | 5916.8214 | 311888.6161 | 332120.8831 | 358725.6297 | 383883.3439 | 412726.3519 | 440914.6787 | 474686.1266 | 506484.1784 | 551972.5489 | 587821.7678 | 628306.8776 | 670093.4937 | 706028.3823 | 739273.4665 | 778981.5634 | 821553.7968 | 862617.6448
Total benefits | [5 empty] | 1860452.0175 | 6742109.5194 | 7130445.4435 | 7738356.1967 | 8265270.543 | 8856091.8729 | 9411003.7532 | 10138767.9247 | 10799275.3895 | 11729639.0683 | 12471603.4616 | 13266840.9456 | 14174119.0698 | 14934934.1657 | 15744661.0535 | 16670962.3422 | 17584829.1777 | 18593602.3376
|  | Project Year |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
|  | Calendcar Year |  | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
annual maintenance | [5 empty] | 880000 | 880000 | 880000 | 880000 | 880000 | 880000 | 880000 | 880000 | 880000 | 880000 | 880000 | 880000 | 880000 | 880000 | 880000 | 880000 | 880000 | 880000
periodic maintenance | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Additional supervision costs in the event of non-completion | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Basic investment |  |  |  | 1 2011: 32.7964; 2 2012: 32.0376
Compact Management/Admin |  |  |  | 1 2011: 7.6538; 2 2012: 7.4767
Incremental Net Benefits |  |  |  | -40.4502 | -39.5143 | 0.98045 | 5.8621 | 6.2504 | 6.8584 | 7.3853 | 7.9761 | 8.531 | 9.2588 | 9.9193 | 10.8496 | 11.5916 | 12.3868 | 13.2941 | 14.0549 | 14.8647 | 15.791 | 16.7048 | 17.7136
| ERR | 8.071%
Incremental Benefits |  |  |  | 0 | 0 | 980452.0175 | 5862109.5194 | 6250445.4435 | 6858356.1967 | 7385270.543 | 7976091.8729 | 8531003.7532 | 9258767.9247 | 9919275.3895 | 10849639.0683 | 11591603.4616 | 12386840.9456 | 13294119.0698 | 14054934.1657 | 14864661.0535 | 15790962.3422 | 16704829.1777 | 17713602.3376
NPV Benefits @ 10% |  | 58131163.3454
Likelihood of Industrial Park |  | 0.5
Expected Return (50% probability of no industrial park; if there is industrial park, equal probability of full anticipated traffic occuring within 4 years after road investment)
Expected ERR |  | 11.45% | 50% probability of no industrial park; 50% probability park within three years of road completion.
PV of Benefit Stream |  | 98518782.9379
Mean ERR assuming indust. park |  | 14.83% | Operating within 3 years of completion of road.
Average trips per person |  | 43 | SVR1 p 3 footnote, Mongolia road statistics
External beneficiaries |  | 65644.6134 | based on estimated passenger numbers of 2/3 of traffic between Choir and rest of Mongolia
|  | Cost Range (UDD/km) | 467600 | 1 2011: 350000; 2 2012: 400000; 3 2013: 450000; 4 2014: 500000; 5 2015: 550000; 6 2016: 600000
|  | ERR when Likelihood of Industrial Park 50/50 | 0.10404 | 1 2011: 0.12958; 2 2012: 0.11778; 3 2013: 0.10741; 4 2014: 0.098185; 5 2015: 0.089891; 6 2016: 0.082372
|  | Likelihood of IP Switching Value or Certainty | N/A | 1 2011: N/A; 2 2012: N/A; 3 2013: N/A; 4 2014: 0.52758; 5 2015: 0.65568; 6 2016: 0.77501
Max ERR with Industrial Park Certainty
|  | Percentage of Road Completed with Budget | 64.16% | 1 2011: 85.71%; 2 2012: 75%; 3 2013: 66.67%; 4 2014: 60%; 5 2015: 54.55%; 6 2016: 50%
Cost allocation worksheet - distribute costs evenly across 2 years
| Compact total costs, |  | Real costs (constant 2011 $, million)
Cost item | current $ | Project Year | 1 | 1 2011: 2
| ($ million) | Calendar year | 2011 | 1 2011: 2012
Construction cost | 74.7759 |  | 32.7964 | 1 2011: 32.0376
Project admin | 5.0517
Program Admin | 12.3989
Total Admin | 17.4506 |  | 7.6538 | 1 2011: 7.4767
Cost share by year |  |  | 50% | 1 2011: 50%
Adjustment to 2009 values, by year |  |  | 1.14 | 1 2011: 1.167
(average of adjustments for foreign and local expenditures)
Additional contingency | 1.7 | See Feb. 10, 2012 memo
Note on A16: derenb: increase in induced traffic on Chor-Sainshand due to full construction of Chor-ZU road
Note on A35: andersonsc: See Lookup table, at right
Note on B33: andersonsc: 24 Dec 2011
Note on B228: derenb: Generated traffic as earlier estimated without impacts of industrial park
Note on B299: Zinvor: Final disbursement amount confirmed by Burak Inac and Rodney Chow, Oct 2014
Note on C10: andersonsc: "Maintenance cost.docx" Attchment to email from Roberto Salgado of Dec. 21, 2011.
Note on C286: derenb: Probability of IP to reach threshold of 10%. If even with certainty the ERR falls below threshold "Certain" is displayed.
Note on D205: andersonsc: PPP conversion based on PPP conversion factor e.g., [S:\_divisions\Economic Analysis\Beneficiary Analysis\Beneficiary Data\Mongolia\Updated BA - Feb 2010\Mongolia Revised BA - 8.12.10.NEW POV CATEGORIES.xls]Health, lines 63-64.
Note on D298: andersonsc: For consistency with above; in reality, this is 2012-2013, so deflate cost amounts accordingly.
Note on K5: derenb: Based on feasibiltiy study estimates
Note on L39: andersonsc: Use this to estimate income increase.
Note on M5: derenb: Based on feasibiltiy study estimates
Note on Q23: andersonsc: Assumed
Note on Q92: derenb: NB this figure appears to be inconsistent with the growth pattern. The series is adjusted below.
Note on R23: andersonsc: Assumed
Run Sensivity

## Poverty Scorecard
Poverty Scorecard
Mongolia
Choir-Sainshand Road Project
MCC Cost (Millions USD) | 74.7759
20-Year ERR | 9.402%
Present Value (PV) of Benefit Stream (Millions USD) | 98.5188
Consumption per day (2005 PPP $)
Beneficiaries | Total | < $1.25 | < $2 1 | $2-$4 | > $4
Beneficiary Households in Year 20 (#) | 37427.6439 |  |  |  |  | Population of Ulaanbaataar |  | 853050
Beneficiary Individuals in Year 20 (#) | 160938.8689 |  |  |  |  | Pop Ulaanbaataar Projection |  | 1104494.0853
National Population in Year 20 2 (#) | 3346951.7736 |  |  |  |  | persons per household |  | 4.3
Beneficiary Population by Poverty Level 3 (%) |  | 0.45% | 3.96% | 25.79% | 69.79% | Local Beneficiary Population |  | 73600 | 2.847%
National Population by Poverty Level 4 (%) |  | 0.46% | 4.19% | 30.09% | 65.26% | Local Beneficiary Pop Projection |  | 95294.2555 | 2.847%
The Magnitude of the Benefits | [5 empty] | External Beneficiary Pop Projection |  | 65644.6134 | 1.961%
PV of Benefit Stream Per Beneficiary (USD) | 612.2116 | 108.8267 | 170.0418 | 279.3722 | 764.3327 | Pop Growth | 1.3%
PV of Benefit Stream as Share of Annual Income | 2.873% | 3.074% | 3.111% | 2.874% | 2.878% | Pop projection | 3346951.7736
Cost Effectiveness
PV of Benefit Stream/Project Dollar (USD) | 1.3175 | 0.001054 | 0.014493 | 0.15507 | 1.1481
[11 empty] | Gross domestic product based on purchasing-power-parity (PPP) per capita GDP | 3566.753 | WEO Oct 2009
[11 empty] | GDP/capita/day | 9.7719
Percent of Project Participants Who Are Female
2510000
GNI per capita 5 (USD) | 1290
Current National Population | 2585000 |  |  |  |  | Mean consumption per person per day (Central Region)
[6 empty] | < $1.25 | $1.25-2 | $2-$4 | > $4
NB: all benefits incremental; PVs based on 10% discount rate and exclude MCC costs but net out any local costs | [5 empty] | 1.14 | 1.76 | 3.13 | 8.55
Calculated from the 2007-2008 household dataset
1 The beneficiaries and population living on less than $2 per day include those under $1.25 per day
2 Based on MCC 2009 Scorecard data, projected to Year 20 | [5 empty] | Distribution of Returns (Central Region, based on household socio-economic data, 2007-2008)
3,4 Based on data from the 2007-2008 Household Socio-economic Survey | [5 empty] | < $1.25 | $1.25-2 | $2-$4 | > $4
5 See MCC 2009 Scorecard | [5 empty] | 0.08% | 1.02% | 11.77% | 87.14%
These distributions correspoind to a Gini of 0.33 provided by PovCalc
[6 empty] | Discounted Current Annual Income Streams over 20 Years | Present Value | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
[6 empty] | <1.25 | 3540.5528 | 415.872 | 415.872 | 415.872 | 415.872 | 415.872 | 415.872 | 415.872 | 415.872 | 415.872 | 415.872 | 415.872 | 415.872 | 415.872 | 415.872 | 415.872 | 415.872 | 415.872 | 415.872 | 415.872 | 415.872
[6 empty] | 1.25-2 | 5466.1166 | 642.048 | 642.048 | 642.048 | 642.048 | 642.048 | 642.048 | 642.048 | 642.048 | 642.048 | 642.048 | 642.048 | 642.048 | 642.048 | 642.048 | 642.048 | 642.048 | 642.048 | 642.048 | 642.048 | 642.048
[6 empty] | 2-4 | 9720.9914 | 1141.824 | 1141.824 | 1141.824 | 1141.824 | 1141.824 | 1141.824 | 1141.824 | 1141.824 | 1141.824 | 1141.824 | 1141.824 | 1141.824 | 1141.824 | 1141.824 | 1141.824 | 1141.824 | 1141.824 | 1141.824 | 1141.824 | 1141.824
[6 empty] | >4 | 26554.1458 | 3119.04 | 3119.04 | 3119.04 | 3119.04 | 3119.04 | 3119.04 | 3119.04 | 3119.04 | 3119.04 | 3119.04 | 3119.04 | 3119.04 | 3119.04 | 3119.04 | 3119.04 | 3119.04 | 3119.04 | 3119.04 | 3119.04 | 3119.04
Note on N49: MCC: NB 30.4 days/month average for consumption