## Toolkit Menu
Land Records & Transaction System - Assessment and Design Toolkit -
STAGES THREE, FOUR and FIVE
Section 3: Final Pre-Approval Details
68 | InvOption | Selection of Final Funding Option
69 | ProcStrat | Procurement packaging and implementation (IEA) arrangements - Identify procurement strategy
70-73 | n/a | Total Cost of Ownership - Refer to Toolkit Forms Basic Costing and TCO
Section 4: Post Approval Detailed Planning and Scoping
75-76 | FuncReqs | What are the functional requirements for the selected option?
77-79 | NonFuncReqs | What are the non-functional requirements for the selected option?
80-86 | ApproachSuit | Suitability of software development approaches
Section 5: Post Approval Rollout Planning
88 | AddDetails | What additional details are critical to planning for implementation of the technology solution?
Guide to users:
- This Workbook series comprises Part II of the Land Records and Transaction System Assessment and Design Toolkit, and accompanies the Part I powerpoint. Whilst Part 1 provides essential guidance on how to use the tool, this Part II provides the worksheets and inbuilt formulas for data collection, collation and analysis.
- Use the hyperlinks in the Menu to the left to navigate directly to a tool, or cycle through the tabs below. If you use a hyperlink, you can use the shortcut F5 or ctrl+G to go back to your previous location.
- USER NOTES are shown in comments on each tool. Comments look like a small purple triangle in the top right corner of a cell:
- Text in red provides guidance and should be replaced with your own text
- Add more lines as necessary

## Option
Selection of Final Funding Option
Return to Toolkit Menu
Selected Funding Option: _______________ | Technology Level _______________
Key technology and systems solution components, as relevant | Detail components/steps, building upon original option
1)
2)
3)
Additional necessary components, addressing legal/institutional and finance/financial sustainability issues not addressed by technology | Detail components/steps, building upon original option
1)
2)
3)
Geographic Scope | Detail whether national, urban/rural and/or which administrative areas to be covered.
CPs/Reform Issues to be addressed | Refer to identified prerequisites/reform requirements:
a)Legal/Institutional and
b)Financial Sustainability
IM-stage (basic) cost + contingency | From basic costing
IEA Roles and Responsibilities for Implementation
IEA budgetary allocation required to support operating costs
Comment re: risk and sustainability | Draw from sustainability and risk assessment
Other selection reasons

## ProcStrat
Procurement packaging and implementation (IEA) arrangements - Identify procurement strategy
Return to Toolkit Menu
Funding Option _________________________
Activity | Applicable - Y/N | Provision by - select from drop down or type in | Provider
Software design and development |  |  | In-house
Procurement of hardware |  |  | Other Govt
Procurement of civil works |  |  | Contractor
Capacity building and training |  |  | Other?
Digitization of existing manual records (including necessary restoration work)
Systems administration
Internet access and/or network arrangements
Base mapping (including digital cadastral mapping, orthophotos and acquisition of satellite imagery)
Business continuity planning
Other consultant services
[other?]

## FuncReqs
What are the functional requirements for the selected funding option?
Return to Toolkit Menu
| Functional Requirements | Comments
Process land administration transactions
£ | Case management of each transaction
£ | Process services according to specific workflow
£ | Calculate fee calculation & record receipts for fees paid
Manage Property Details
£ | Retrieve property details
£ | Retrieve property history of transactions
£ | Retrieve scanned images of supporting documents for transactions (past and current)
£ | Edit property details (corrections & refinements)
Manage Spatial Units (Parcels)
£ | Support subdivision/split of parcels service
£ | Support merge parcels service
£ | Support redefine/correct parcel boundaries service
£ | Support for other spatial units (e.g. easements, land to be acquired, assessment units etc)
Manage Spatial Information
£ | Search and view spatially defined cadastre objects
£ | Search property/parcel and transaction details spatially
£ | Display other spatial map layers
Manage Rights, Restrictions & Responsibilities (RRR)
£ | Support registration & recording services
£ | Support services to cancel registration or recording of RRR
£ | Support the recording of RRR rightsholders (including changes to rightsholder details)
£ | Support mass systematic registration (including the bulk loading of completed systematic registration records)
Manage Digital Document Archive
£ | To store (for easy retrieval) scanned images of documents supporting a transaction
£ | Link these scanned images to the requested service and the appropriate properties
£ | Search and retrieve document images stored in the digital document archive
£ | Bulk loading of scanned historic land records
Generation of certificates and reports
£ | Generate certificates that have been customized to meet local legal requirements and language
£ | Generate client search products (including those with maps)
£ | Generate notifications associated with land administration services
£ | Auto generate email (or SMS) notifications to applicant / owner when key milestones of a service are passed
£ | Generate office (or staff member specific) transaction processing metrics report
Linkages with other IT systems within land agency
£ | Land Lease system / Finance system
£ | Mapping system
£ | Document management system / Land Record Digital Archive
£ | Mass systematic registration system
£ | Other
Linkages with external systems
£ | Taxation Office system
£ | Citizen ID system
£ | Other
Other functional requirements not identified above

## NonFuncReqs
What are the non-functional requirements for the selected funding option?
Return to Toolkit Menu
| Non-functional Requirements | Comments
System Security
£ | User authentication
£ | User role management including managed access to perform certain functions and view certain database and archive details
£ | Logging of all changes to critical data elements
£ | Ability to audit database changes and system access
£ | Land agency network protected by firewall (if there is external connectivity)
£ | SSL (TLS) encryption between server hosting web application and client computers (if technology involves a web application accessed via the internet)
Software maintainability
£ | Commitment to updating land records and transaction system and/or related technology software including dealing with newly identified security vulnerabilities
£ | The ability for land agency (system support) to maintain reference data / code lists
£ | The ability for land agency (system support) to modify business rule logic including validation routines and workflow logic
£ | Support for refining language localizations in any software
Software portability
£ | Specify the operating system(s) required on the server and client computers
£ | Specify the web browsers to be used on client computers
£ | Specify application server
£ | Specify which Database Management System (DBMS)
£ | Specify report generation app
£ | Specify geospatial mapping app
£ | Specify related mobile applications and the means of data exchange
£ | Specify the means of deployment | Desktop app, local client-server, web client server, local server but “cloud ready”, cloud. Docker – non Docker
User Interface
£ | Style of user interface
£ | Layout of Dashboard
£ | Help function
Standards to be adopted
£ | Land Administration Domain Model (LADM) ISO 19152:2012 – database design
£ | Simple Feature Access Part 2 SQL Options (ISO 19125:2004) - database spatial definitions & associated SQL queries
£ | Geographic Markup Language (GML) – spatial data interchange
£ | PDF/A ISO 19005 – scanned land records
£ | Unicode – for certain language scripts
£ | JSON ISO/IEC 21778:2017 for interchange of data between mobile devices and servers/workstations
£ | HTTPS RFC 2818 – for safe & secure access to web applications via the internet
£ | National Unique Parcel Identifier – in parcel related records
£ | Other
Other functional requirements not identified above

## ApproachSuit
Suitability of Software Approaches
Return to Toolkit Menu
Suitability of a BESPOKE software development option
Suitability Question | Responses |  |  | Additional Comment/ Justification
| GREEN | ORANGE | RED
Are there software development providers with the right expertise and experience prepared to engage with the land agency to develop the required software solution and, in the longer term to support the software solution? | ____Team has appropriate expertise and experience and it is possible to recruit further software developers locally | ____Team might not have expertise or experience necessary for proposed investment but it is possible to recruit further software developers locally | ____No
Is there in-house capability within the land agency to manage this software development or could a suitably experienced consultant (ideally local) be recruited to assist the land agency in this role? | ____ Yes, including someone trained in a modern software development methodology | ____ Yes but software development methodology training required OR an external (local) consultant recruited for the project | ____ No and it would be difficult to recruit someone locally
Does the land agency commit to make available to the software development provider staff members expert in the business processes impacted by the proposed investment to elaborate the functional requirements and participate in user acceptance testing ? | ____ Yes | ____ Yes, but laptops and internet connectivity may need to be arranged (for communications between these land agency staff and the software developer provider etc) | ____ No
Suitability of an IN-HOUSE software development option
Suitability Question | Responses |  |  | Additional Comment/ Justification
| GREEN | ORANGE | RED
Is there an existing in-house team of software developers and can that team be augmented by recruiting contractors or new staff? | ____Team has appropriate expertise and experience and it is possible to recruit further software developers locally | ____Team might not have expertise or experience necessary for proposed investment but it is possible to recruit further software developers locally | ____ No
Is there in-house capability to manage this software development? | ____ Yes, including someone trained in a modern software development methodology | ____ Yes but software development methodology training required OR an external (local) consultant recruited for the project | ____ No and it would be difficult to recruit someone locally
Is the extension or upgrade of one of the existing LRT IT systems developed or supported by the in-house software developer team considered a potential technology solution for the proposed investment? | ____ Yes | ____ Yes, but upskilling of the in-house team would be required | ____ No and the necessary expertise and experience is lacking in the in-house team and not easily remedied
Are the existing LRT IT systems developed by the in-house software developer team considered to be ”well constructed” ? | ____ Yes | ____ No, but in-house team could be up-skilled and with better leadership is capable of developing “well constructed” software for the proposed investment | ____ No, and upskilling in the timeframe of the proposed investment is not likely
Is the experience gained from developing (or supporting) an existing LRT IT system relevant to the software development envisaged in the proposed investment ? | ____ Yes | ____ Yes but some upskilling or recruitment of software developers with particular skills would be necessary | ____ No
Suitability of a COTS software development option
Suitability Question | Responses |  |  | Additional Comment/ Justification
| GREEN | ORANGE | RED
Are there COTS offerings that meet the system requirements for this proposed investment? | ____There is a complete match of all critical requirements (potentially involving configuration) & the remaining requirements can be met through customization of the software | ____Customization is required to meet critical requirements | ____There are critical requirements that cannot be met
Do the COTS providers have a local agent with software support capacity ? | ____ Yes | ____ Yes but there is no previous association with the land agency | ____ No
OR
there is a local agent but previous associations with the land agency (or other local organizations have not been constructive
OR
previously the local agent has not been well supported by the COTS provider
Are the COTS providers able to provide firm costing of licence fees and software support to the land agency for first 5 years of post Compact operation of the software provided? | ____ Yes | ____ No, but there is a willingness to negotiate | ____ No and there is a history of price hikes when development assistance ends
Suitability of a MONOLITH software architecture
Suitability Question | Responses |  |  | Additional Comment/ Justification
| GREEN | ORANGE | RED
Each land agency office will operate a discrete stand-alone system (on either a single workstation or server and local area network) ? | ____Yes |  | ____No
Continuous, reliable internet connectivity is not available nor is continuous internet connectivity required to meet software requirements? | ____ Continuous internet not required or is not available | ____ Yes providing occasional internet is available for system support | ____ No, internet connectivity is required to meet software requirements
This will be : | ____ If all these conditions apply | ____ If a simple data exchange mechanism is sufficient to achieve a system linkage requirement | ____ No (if one or more of these conditions do not apply)
• the first computerized LRT IT system in the land agency,
AND
• software development will be undertaken using relatively inexperienced developers
AND
• there are no requirements for system linkages (internal or external)
AND
• Software requirements indicate software complexity is low
Are the currently stated system requirements likely to change ? | ____ The land agency is strongly committed to these requirements & they are likely to remain highly relevant for at least the next 5 years | ____ These requirements are likely to remain relevant for at least the next 5 years | ____ Not known OR the land agency (or public sector generally) are subject to significant change OR there is a chaotic environment
Suitability of a SOA software architecture
Do the requirements include linkages to other systems (local or external) ? | ____Yes |  | ____No
Do some of these factors apply: to this new LRT IT system? | ____ If all of these factors apply | ____ If some of these factors apply | ____ If none of these factors apply)
• this is the first computerized LRT IT system in the land agency,
• software development will be undertaken using relatively inexperienced developers
• software requirements indicate software complexity is low – moderate
• system will contain records for more than 100,000 parcels (or land titles or properties etc)
• a system upgrade to incorporate more functionality in the next 3 years is likely
Suitability of a MICROSERVICES software architecture
Suitability Question | Responses |  |  | Additional Comment/ Justification
| GREEN | ORANGE | RED
Is this new system an upgrade of an existing LRT IT system ? | ____Yes | ____ No, but there is significant local microservice architecture software development experience | ____No
Is there significant local microservice architecture software development ? | ____Yes | ____ No, but local software developers involved can be up-skilled | ____No
Is continuous, reliable internet connectivity available ? | ____Yes |  | ____No
Do software requirements indicate software complexity is moderate – high? | ____Yes | ____ No, but there is significant local microservice architecture software development experience | ____No
Suitability of a SERVERLESS architecture
Suitability Question | Responses |  |  | Additional Comment/ Justification
| GREEN | ORANGE | RED
Is continuous, reliable internet connectivity available? | ____Yes |  | ____No
Are there any legal or policy constraints on the use of cloud servers located in another country? | ____Yes | ____ if the legal or constraint can be changed to allow such use within a timeframe that does not delay implementation of the new system | ____No
Is there international consensus and standards covering the implementation of server-less architecture? | ____Yes |  | ____No
Is this new system an upgrade of an existing LRT IT system? | ____Yes | ____ No, but there is significant local server-less architecture software development experience | ____No
Is there significant local server-less architecture software development experience? | ____Yes | ____ No, but local software developers involved can be up-skilled | ____No
Do software requirements indicate software complexity is moderate – high? | ____Yes | ____ No, but there is significant local microservice architecture software development experience | ____No
Tool to assess suitability of LAAS Software + O&M option
Suitability Question | Responses |  |  | Additional Comment/ Justification
| GREEN | ORANGE | RED
Can reliable and affordable internet be provided in all land agency offices where land administration transactions and services are initiated, processed or delivered ? | ____Suitable internet is available in all land agency offices | ____Suitable internet will be available in some land agency offices during first half of the Compact | ____Suitable internet will not be available until at least the second half of the Compact
Is there suitable LAN, power & other land office infrastructure or can it be sufficiently upgraded? | ____ Suitable reliable infrastructure exists | ____ infrastructure can be upgraded or undertaken as part of the preparations for the proposed investment | ____ It is not certain when infrastructure will be adequately upgraded
What is the state of maturity of LAaaS offerings? Are there LAaaS offerings that meet the system requirements for this proposed investment? | ____ There is a complete match on all highly ranked requirements & most of the remaining requirements | ____ All critical requirements can be met | ____ There are critical requirements that cannot be met
Are the currently stated system requirements likely to change ? | ____ The land agency is strongly committed to these requirements & they are likely to remain highly relevant for at least the next 5 years | ____ These requirements are likely to remain relevant for at least the next 5 years | ____ Not known OR the land agency (or public sector generally) are subject to significant change OR there is a chaotic environment
Is there experience within the client government in managing similar ”As a Service” arrangements ? | ____ Yes there is experience and it has been a positive experience | ____ Yes there is experience but experience has been mixed | ____ No
Are there any legal impediments to computerization of land administration transaction processing or government “As a Service” arrangements? | ____ No | ____ Yes, but any impediments can be accommodated | ____ Yes

## AddDetails
What additional details are critical to planning for implementation of the technology solution?
Return to Toolkit Menu
Funding Option: _____________________________________
Topic |  | Describe key issues and likely risks/ | Potential Solutions | Required Strategy or Plan
Business processes
Business process reform | Describe the business activities directly involved in or are impacted by the investment option and technology solution. |  | What are the operational issues likely to be encountered in implementing the investment option and technology solution? | What is the most appropriate approach
|  |  | What is the logic behind business rules that could be incorporated into the computerized system as automated validation checks? | E.g. the identification of the initial revised workflow(s) to incorporate computerized support with detailed workflows developed as part of system design and system implementation planning OR an organization-wide BPR as a prerequisite to any system development ?
What roles (to view records, to edit records to validate transactions or to approve transaction or to administer the system need to be included in the computerized system
Proposed timeline to implement investment option business process changes
Business continuity | Likely risks/challenges to business continuity |  | E.g. What steps will need to run in parallel with both paper based processing and computer supported processing and for what length of time? | Overarching strategy vs. temporary measures that may be needed (e.g. legislation, staffing, office space) for transitional period
| E.g. Transition needs E.g. Possible system downtime due to system implementation and/or risk of malfunction |  | E.g. Strategy for regular, data back-up regimes and processes to restore from backups | Comprehensive new system disaster recovery plan which is regularly reviewed and processes are trialled by system administrators
| E.g. Excessive staffing workloads and any resulting transaction processing backlogs during transition period |  | E.g. Alternative power or communication linkages.
| E.g. System downtime when new system is operational and mitigating actions to limit impact |  | E.g. Ability to store transaction processing details and data changes locally and upload later when communication linkage is re-established
E.g. Inadvertent and malicious user data entry mistakes impacting on the integrity of the new systems database
E.g. interruption to power supply or failures in system linkages (including internet, if applicable)
E.g. natural (and other) disasters
Digitisation | Land records systems requiring digitisation: |  | Comment on any likely logistical challenges | Digitization Plan
| Name - location - # records - % of total requiring digitisation |  | Comment on minimum necessary scope | Digitization training material
Migration of data from legacy system(s) |  |  | E.g. describe data format and quality of legacy data | Data Migration Plan
E.g. describe Export data format and how Export will be generated and when
Training and Capacity building | Refer to details in Legal and Institutional information gathering. |  |  | User training plan and training material
System administration training plan and training material